## ESS
S.No | Pending Implemetation | Remarks | Protiviti Commenet | Protiviti remarks | RML Comment
1 | Compensation structures,current and previous financial years for seamless continuity. | 70, 80, 90 % compensation structure | Completed |  | >Probation % salary breakup (70%, 80%, 90%) and confirmation salary breakups should be automated. > Auto configuration and not reflecting in offer.
2 | Roles & Responsiblities of deployed employees-Protiviti |  | Completed |  | Access control matrix of protiviti employees not recivied
3 | Assistance in Defining Multiple Pay Structures based on job grades, levels, and locations. | Pay structure to be implemented. | Completed |  | Pay structure should be auto confiqured
4 | Platform Dashboard for HR and management reporting. | Auto alerts | Completed |  | Not done
5 | Real-Time Policy Acknowledgement Tracking and automated alerts for non-compliance. |  | Completed |  | Dashboard & auto alerts not done
6 | Offer letter generation and approvals. | Offer genaration | Completed | Approvals is asked by Anirban to not include as it is part of ATS in workday | Offer approval is not set up
7 | Employee loan processing on ESS portal and approval workflow. |  | Completed |  | >Existing employee loan details not updated. >It should not open for all employess > Workflow to be configured
8 | Probation review tracking and automated reminders. | Probation reminder to be implemented | Completed |  | Auto alerts not coming
9 | Flexi-Basket Benefits, Reimbursements, and Employee Investment Declarations. |  | Completed | Investment Declration to be opened after Aug'25 payroll closer. Flexi is not part of RML current salary structure | Investment Declration to be opened
10 | Multi-Level Approval Workflows for Employee Confirmation. |  | Completed |  | Showcase
11 | Resignation Initiation, Tracking, and Approval Workflows. |  | Completed |  | Final workflow not confiqured in proper way. Not visible to Chaitanya
12 | Automated Alerts for Absenteeism, Late Arrivals, and Early Departures. |  | Completed |  | Auto alerts not coming for UAB across the hirearchy & HR as discussed.
13 | Overtime Tracking Based on Pre-Approved Policies. | OT policies to be implemented |  | This is working with a work around solution where Protiviti team is sending OT for approvals with heads. Once confirmation is received it is processed along with payroll | A pre approved system approval to be configured as per the requirent given during setup
14 | Platform alerts for , regularization requests, and policy violations. | Auto reports and alert | Completed |  | Alerts not working
15 | Tax Computation Based on Employee Investment Declarations via ESS Portal. | To be enabled | Completed |  | To be enabled
16 | Employee Feedback Surveys for Continuous HR Improvement. | To be done | Completed |  | That has to be done

## Payroll
S.No | Pending Implemetation | Remarks
1 | Payroll | If an employee is completely absent for the month. > That weekly offs are should not be credited or paid to employees who are absent for the entire month > Weekly off not to be credited or paid for employees who are on UAB (Unauthorised Absentee) for the entire week
2 | Unauthorized absence rule | No weekly off should be provided if the employee is absent without authorization for all 6 working days in a week.
3 | Compliance issues | PF, ESIC, and PT tax-related issues need to be fixed.(Calculation)
4 | Reports | Configuration of required reports to be completed.
5 | Full & Final (F&F) Processing | Configuration to be verified, checked, and finalized.
6 | Leave credits | Streamline the process for accurate leave crediting.
7 | Employee Master Data | Ensure employee master records and exit cases are updated accurately.
8 | Reporting Manager field | Functional Reporting Manager’s name should be included in the master report.
9 | Offer Management | Offer letter and approval process configuration to be completed.
10 | PaySlips | Template is different for the month of may m june and july , after reminder and email , no action has been taken.