## Sheet1
ERP | OEM |  | STATUS | Next Steps 30/4 | SUPPORT
UPCOMING ERP
Manufacturing Execution systems | SIEMENS | Dubey / Shanmuka / Reddy | Excluding rockwell , all quoted Aveva quoted highest @ Rs 56 Cr in 3 yrs on cloud version. on server 50-60% decrease . | CFO and SK sharma Sir has called them at kGP for understanding and negotiation on 5th May 2024. Meeting of AVEVA and ISP Pawan Moore completed. MOM:
AVEVA
GE VERNOVA
ROCKWELL AUTOMATION
FINANCIAL ERP | ORACLE | Karthik / Harsh | Oracle quoted Rs 9 Cr in 3 yrs , IP quote excluded |  | New CIO and IT head to take call
FLEET TELEMATICS | MOBA | Karthik / Harsh | Sent sample equipment at site for Demo , Installer will reach by 1st May to KGp | Installation and demo by 2nd May .
| FRETRON | Karthik | after succesful demo, we will integrate MOBA with Fretron
Procure to Pay | GEP | Arjun | Shared all data with CPO, Meeting schedule awaited
Forecasting and planning | BLUE YONDER | Dubey | Planning head met both , awaiting revised offer for DIP + Seamless
| O9 | Dubey
MISC ERP | THIRD EYE | Harsh/Aritra/Sharique |  | Ai cameras to caputure safety equipment and tag them to Contractors . demo
ONBOARDED ERP
CRM | MONDAY | Aman | No reply / roadmap. Forecasting demo failed. Export leadership aligning pipedrive CRM for export | Leadership intervention required
CRM | MS DYNAMICS | Aman
CRM | SALESFORCE | Aman
HRMS | WORKDAY | Ayush | On track , Core HCM and recruting to go live by aug 2025. Foundation sessions is in progress
FDMS | MOBA | Karthik / Harsh | DEMO and pilot is successful, accepted by BUs. Data reconciled and shared for feedback. | final demo for 4 pm
TMS | Fretron | Karthik | Outbound -43% live , delayed due to SAP integrations. Warning issued for 30th Apr deadline to complete all development
OUTSOURCED SERVICES
Quality Management Outsourcing | SGS - BIOCHAR | Shanmuka | Tracking of manpower to start
| SGS - BIOMASS | Shanmuka | Tracking of manpower ongoing | meeting with Suraj / JJ pending
| SGS - DIP | Reddy | Tracking of manpower/ SOW on going | meeting with SGS DIP 1730 hrs
House Keeping | Sodexo - RML 1 Office | Sharique | Agreement fwded to admin for sign off
Plant Safety | SGS - RML 6 | Sharique | Tracking of manpower/ SOW on going | Meeting with safety head at 5 pm today
Contractual Labour Compliance and Management | AparaJitha Emsphere | Arjun | Patra je and Abhishek jee approved emsphere over aparajitha . Financial nego pending with CFO and commercial head on 30th 1030 with emsphere. Awaiting time from aparajitha
Employee transport Management | REGO | Aritra | Warning mail sent for 30th Apr as deliverables not complete | on calls bills may be released on proper reconciliation , awaiting meeting from REGO and zubeen
Payroll | Protiviti | Jyoshna | On track

## 12th May (hidden)
ERP | COMPANY | PRIMARY | BUSINESS USER | Ceo Sir Advise / Suggestion | Current Status - 6th May | Current Status - 12th May
MES | AVEVA | DUBEY / SHANMUKA | PATRA SIR | Immediate Meeting of AVEVA and Mr Pawan | Meeting of AVEVA and Pawan Moore completed on 6th May on implement MES in upcoming 45 MW thermal power plant at RML-6 and efficiency improvements in boiler and turbine performance monitoring.
|  | DUBEY / SHANMUKA |  | Use any certified cloud other MS azure. Price is extremely high | 6th May AVEVA met GM power plant only . 7th May with Planning Head / Seamless Head . 8th May with CFO / Plant head / Project head / production Head / commercial head / maintenance head. | they will share their rock bottom quote by 13th May with complete break up of their BOQ
PLanning & forecasting | BY /o9 | DUBEY / SHANMUKA | PREM SIR | quotation | BY / Deloitte has shared technical offer for seamless and DIP . o9 Will share technical offer by 10th May . o9 visiting plant on 14th May | BY / Deloitte has shared technical offer for seamless and DIP . o9 Will share technical offer after plant visit. o9 visiting our plant on 13th May
| AVEVA |  | PREM SIR |  |  | On 16th May, they will provide a demo to Planning head in line with archiitecture shared by BY/o9
CONTRACT LABOUR AND COMPLIANCE OUTSOURCE | EMSPHERE | ARJUN | ANU SIR | Close immediately | today emsphere team already at KGp to meet CFO / commercial head and plant head to negotiate and close | Price negotiated and finalised by CFO and commercial Head. Rs 12.76 lac per month for 7000 labourers. Final evaluation also done by anjan and Plant head. Next agreement and SOW to be finalised by 14th May. they will initiated deployment 10 days post PO issuance.
ERP | ORACLE | KARTICK / HARSH | ANUP SIR | Anup jee to meet Oracle team and understand | Awaiting meeting schedule with Anoop jee | meeting sir on zoom call on 14th may 1530 hrs IST
TELEMATICS | MOBA | HARSH / ARITRA | ANURAG | Physical meeting | MOBA telematics equiments installed in two demo vehicles for fluel and net hrs monitoring on 3rd May . portal linked by 5th May. Awaiting demo date at kharagpur | MOBA telematics equiments installed in two demo vehicles for fuel and net hrs monitoring on 3rd May . portal linked by 5th May. Awaiting demo date at kharagpur
FUEL dispensing | MOBA | HARSH / KARTICK | SARANGI SIR | Bowser Fuel reco required , take quotation from vendor / immediate ohysical meeting | MOBA awaiting for date from mgmt when to come to KGp for final demo | Data fwded to Automobile head for inputs on 12th May
Visual Ai | THIRD EYE |  |  | demo --> reco then order against 50% BG | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) Tata Mines ( Joda) ( Moisture quality inspection) Tata Iron ( JODA) - Safety Gear, Man Machine Interface IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) Adani - Odisha mines ( Wagon and Safety Gear) JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) Awaiting demo date | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) Tata Mines ( Joda) ( Moisture quality inspection) Tata Iron ( JODA) - Safety Gear, Man Machine Interface IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) Adani - Odisha mines ( Wagon and Safety Gear) JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) Awaiting POC date
ENGINEER DRAWING MANAGMENT SYSTEM | WRENCH Solns |  |  |  |  | discovery call awaited . they also provide end to end project mgmt soln
Procure to Pay | GEP | ARJUN | SANJAY SIR | CPO to take call after his whole team joined | CPO to meet GEP over zoom on 8th May 2 pm | Initial meeting completed with CPO. Revised NDA being signed. GEP to visit plant to understand our process once CPO advise
CRM | MS Dynamics | AMAN | MR GEORGE | immediate meeting | MS dynamics team will provide demo on our data on 9th May | Demo completed with . Awaiting license and implementation cost.
| Salesforce | AMAN | MR GEORGE | immediate meeting | Discovery meeting completed with new team. Salesforce has shared list oi partners with manufacturing experience . once partner finalized demo will be initiated | Previous Engagement in place with a detailed SOW. Partners selected by Mr george. Customized demo will follow.
| PIPEDRIVE | AMAN | MR GEORGE |  |  | Virtual meeting scheduled on 14th May 2025 at 15:45 hrs IST, as advised by you.
HRMS | Workday | AYUSH |  | payments terms to align with Deloitte | Discussion with Anup jee and WD is completed on 1st May. awaiting feedback from WD | meeting with WD today at 1600 hrs
| Deloitte | AYUSH |  |  | Project planning and documentation completed by 20th Apr. Design phase for Core HCM and recruitment is in progress | Implemetation progress at 5% as per the whole project. As discussed with Delloite as agreed they will complete phase 1 - Core HR and recruitment module by Aug 25
TMS | FRETRON |  |  |  | Progress review as per agreement tracker on 27th April | Progress review as per agreement tracker on 13th May
SAFETY | SGS |  |  | Daily obs and sol MIS (min 50 nos) / ISSUE MAIL TO SGS | Progress review as per agreement tracker done on 25th april. | Progress review as per agreement tracker on 13th May
Employee Transport | REGO |  |  | Over utilization soln and employee on boarding in vehicle MIS / cash pick agency to be hired 2 parking lots to be provide to rego immediately to save 40km / day. self driven 10 vehicles to be procured dispose HO vehicles / emergency pool 1-2 car to be kept in RML 6 at night / housing to factory 1-2 vehicles to run all day / uber tie up | real time utilization being maintained. List of issues from rego end being listed On call booking demo pending /QR based boarding demo pending On call Mar and apr bill process under audit as per REGO agreement tracker they are at 47% Vehicle wise manpower list to be shared by admin team | Progress review as per agreement tracker on 13th May
PAYROLL | Protivity | AYUSH |  | Salary thru them by May end | 2 resources deployed at site / data transfer from RML side is complete / ready for onboarding from 12th May | 3 resources deployed at site / data transfer from RML side is complete / onboarding from 12th May / Final UAT by 31st May
QUALITY BIOMASS | SGS | SHANMUKA |  |  | Progress review as per agreement tracker done on 25th april. | Progress review with Biomass stakeholders will be done on 14th May
QUALITY BIOCHAR | SGS | SHANMUKA |  |  |  | Progress review with Biochar stakeholders will be done on 14th May
QUALITY DIP | SGS | REDDY |  | ISSUE MAIL TO SGS | Progress review as per agreement tracker done on 25th april. | Progress at 11% . SGS RM taken 1 month time from management
LAPTOP AND DESKTOP MIS | DELL / MAC BOOK |  |  |  | Will collate data from IT team and share report by today. basic webpage will be ready by 10th May | IT data received and IT ticketing MIS submitted. payment released . IT asset MIS required by 14th May

## 13th May
ERP | COMPANY | PRIMARY | BUSINESS USER | Ceo Sir Advise / Suggestion | Current Status - 6th May | Current Status - 13th May
MES | AVEVA | DUBEY / SHANMUKA | PATRA SIR |  | Meeting of AVEVA and Pawan Moore completed on 6th May on implement MES in upcoming 45 MW thermal power plant at RML-6 and efficiency improvements in boiler and turbine performance monitoring.
|  | DUBEY / SHANMUKA |  | Comparative with other Vendors. Target for 3 yrs is 18-19 Cr | 6th May AVEVA met GM power plant only . 7th May with Planning Head / Seamless Head . 8th May with CFO / Plant head / Project head / production Head / commercial head / maintenance head. | AVEVA will share their rock bottom quote by 13th May with complete break up of their BOQ . Cost break up asked for GE too
PLanning & forecasting | BY /o9 | DUBEY / SHANMUKA | PREM SIR |  | BY / Deloitte has shared technical offer for seamless and DIP . o9 Will share technical offer by 10th May . o9 visiting plant on 14th May | BY / Deloitte has shared technical offer for seamless and DIP . o9 Will share technical offer after plant visit. o9 visiting our plant on 13th May
| AVEVA |  | PREM SIR |  |  | On 16th May, they will provide a demo to Planning head in line with archiitecture shared by BY/o9
CONTRACT LABOUR AND COMPLIANCE OUTSOURCE | EMSPHERE | ARJUN | ANU SIR | Immediate sign off thru Business user. Agreement checking | today emsphere team already at KGp to meet CFO / commercial head and plant head to negotiate and close | Price negotiated and finalised by CFO and commercial Head. Rs 12.76 lac per month for 7000 labourers. Final evaluation also done by anjan and Plant head. agreement and SOW to be finalised by 14th May. they will initiated deployment 10 days post PO issuance.
ERP | ORACLE | KARTICK / HARSH | ANUP SIR | Commercial comparision with SAP and Oracle | Awaiting meeting schedule with Anoop jee | meeting anup sir on zoom call on 14th may 1530 hrs IST
TELEMATICS | MOBA | HARSH / ARITRA | ANURAG | Final demo with MD Sir | MOBA telematics equiments installed in two demo vehicles for fluel and net hrs monitoring on 3rd May . portal linked by 5th May. Awaiting demo date at kharagpur | MOBA telematics equiments installed in two demo vehicles for fuel and net hrs monitoring on 3rd May . portal linked by 5th May. Moba requested for meeting on 19th Mon / 20th Tue
FUEL dispensing | MOBA | HARSH / KARTICK | SARANGI SIR | ATG to be installed / final demo with MD sir | MOBA awaiting for date from mgmt when to come to KGp for final demo | Data fwded to Automobile head for inputs on 12th May
Visual Ai | THIRD EYE |  |  | Visit adani plant | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) Tata Mines ( Joda) ( Moisture quality inspection) Tata Iron ( JODA) - Safety Gear, Man Machine Interface IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) Adani - Odisha mines ( Wagon and Safety Gear) JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) Awaiting demo date | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) Tata Mines ( Joda) ( Moisture quality inspection) Tata Iron ( JODA) - Safety Gear, Man Machine Interface IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) Adani - Odisha mines ( Wagon and Safety Gear) JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) Awaiting roadmap for POC
ENGINEER DRAWING MANAGMENT SYSTEM | Multiple vendors |  |  |  |  | discovery call being done. some ppt received
Procure to Pay | GEP | ARJUN | SANJAY SIR |  | CPO to meet GEP over zoom on 8th May 2 pm | Initial meeting completed with CPO / SAP. Revised NDA being signed. GEP to visit plant to understand our process once CPO advise
CRM | MS Dynamics | AMAN | MR GEORGE | Target date required | MS dynamics team will provide demo on our data on 9th May | Demo completed with . Awaiting license and implementation cost.
| Salesforce | AMAN | MR GEORGE |  | Discovery meeting completed with new team. Salesforce has shared list oi partners with manufacturing experience . once partner finalized demo will be initiated | Previous Engagement in place with a detailed SOW. Partners selected by Mr george. Customized demo will follow.
| PIPEDRIVE | AMAN | MR GEORGE |  |  | Virtual meeting scheduled on 14th May 2025 at 15:45 hrs IST, as advised by you.
HRMS | Workday | AYUSH |  |  | Discussion with Anup jee and WD is completed on 1st May. awaiting feedback from WD
| Deloitte | AYUSH |  | Need ppt of data shared | Project planning and documentation completed by 20th Apr. Design phase for Core HCM and recruitment is in progress | Implemetation progress at 5% as per the whole project. As discussed with Delloite as agreed they will complete phase 1 - Core HR and recruitment module by Aug 25.
TMS | FRETRON |  |  | BU to do review and show MIS | Progress review as per agreement tracker on 27th April | Progress review as per agreement tracker on 13th May
SAFETY | SGS |  |  | Mail to be sent to SGS | Progress review as per agreement tracker done on 25th april. | Progress review as per agreement tracker on 13th May
Employee Transport | REGO |  |  | Anu sir to meet REGO MD | real time utilization being maintained. List of issues from rego end being listed On call booking demo pending /QR based boarding demo pending On call Mar and apr bill process under audit as per REGO agreement tracker they are at 47% Vehicle wise manpower list to be shared by admin team | Progress review as per agreement tracker on 13th May
PAYROLL | Protivity | AYUSH |  | Need ppt of data shared | 2 resources deployed at site / data transfer from RML side is complete / ready for onboarding from 12th May | 3 resources deployed at site / data transfer from RML side is complete / onboarding from 12th May / Final UAT by 31st May
QUALITY BIOMASS | SGS | SHANMUKA |  |  | Progress review as per agreement tracker done on 25th april. | Progress review with Biomass stakeholders will be done on 14th May
QUALITY BIOCHAR | SGS | SHANMUKA |  |  |  | Progress review with Biochar stakeholders will be done on 14th May
QUALITY DIP | SGS | REDDY |  | Mail to be sent to SGS | Progress review as per agreement tracker done on 25th april. | Progress at 11% . SGS RM taken 1 month time from management
LAPTOP AND DESKTOP MIS | DELL / MAC BOOK |  |  |  | Will collate data from IT team and share report by today. basic webpage will be ready by 10th May | IT data received and IT ticketing MIS submitted. payment released . IT asset MIS required by 14th May

## 21st May
ERP | PRODUCT COMPANY / SUPPLIER | RML SPOC | DEPTS INVOLVED | ERP STATUS | RAG | BUSINESS USER | TCKR | Ceo Sir Advise / Suggestion | Current Status - 6th May | Current Status - 21st May | SUPPORTING DOCS | CHALLENGES | NEXT STEPS / SUPPORT REQUIRED | TARGET
MES | AVEVA | DUBEY / SHANMUKA | SEAMLESS/DIP / PROJECTS | TECHNICAL & COMMERCIAL EVALUATION |  | PATRA SIR |  | Comparative with other Vendors. Target for 3 yrs is 18-19 Cr | 6th May AVEVA met GM power plant only . 7th May with Planning Head / Seamless Head . 8th May with CFO / Plant head / Project head / production Head / commercial head / maintenance head. | AVEVA gave tentative price of 30 Cr including cloud storage. Complete BOM will be provided by 17th May. Received GE's breakdown of 19 Cr offer on 27th May. | LINK | Delay by Vendors on commercial BOM | Technical comparative | 25th May techno commercial comparative to be closed
PLANNING & FORECASTING | BY /o9 | DUBEY / SHANMUKA | PLANNING | TECHNICAL EVALUATION |  | PREM SIR |  |  | BY / Deloitte has shared technical offer for seamless and DIP . o9 Will share technical offer by 10th May . o9 visiting plant on 14th May | BY / Deloitte has shared technical offer for seamless and DIP . o9 visited our plant on 14th May. o9 Will share Techno-Commercial offer by 23rd may and final demo by 29th may. | LINK |  | after finalization of technical offer, quotaion will be recvd | 30th May
PLANNING & FORECASTING | AVEVA | DUBEY / SHANMUKA | PLANNING | DICOVERY PHASE |  | PREM SIR |  |  |  | Discussion and understanding in progress with planning head . Aveva team shared some use cases regarding planning on 20th may. | LINK |  | Demo 20th May | 30th may
CONTRACT LABOUR AND COMPLIANCE OUTSOURCE | EMSPHERE | ARJUN | RML1 & 6(DIP)/BIO MASS/ISP/PRE-CAST/FITTING/SEAMLESS/NITRILE/LATEX | CONTRACT NEGOTIATION & SIGNING |  | ANU SIR |  | Immediate sign off thru Business user. Agreement checking | today emsphere team already at KGp to meet CFO / commercial head and plant head to negotiate and close | Price negotiated and finalised by CFO and commercial Head. Rs 12.76 lac per month for 5000 labourers. Final evaluation also done by anjan and Plant head. agreement and SOW to be finalised by 14th May. they will initiated deployment 10 days post PO issuance. | LINK | Anu sir is already burdened with other ERPs . He requested for anoth BUs | Once BU is alloted, will call the vendor for sign off . Contract nego in progress | 30th May |  | 2490000 | 8545200 | 13248000
ERP | ORACLE | KARTICK / HARSH | FINANCE / SAP / PWC | TECHNICAL & COMMERCIAL EVALUATION |  | ANUP SIR |  | Commercial comparision with SAP and Oracle | Awaiting meeting schedule with Anoop jee | meeting with anup sir today at 2230 hrs. Oracle vs SAP commercial and module wise comparative required | LINK | CIO and IT head to join | Anup Sir will understand our uses case |  | PEPM | #REF! | #REF! | #REF!
[17 empty] | #REF! | #REF!
TELEMATICS | MOBA | HARSH / ARITRA | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | ANURAG |  | Final demo with MD Sir | MOBA telematics equiments installed in two demo vehicles for fluel and net hrs monitoring on 3rd May . portal linked by 5th May. Awaiting demo date at kharagpur | MOBA telematics equiments installed in two demo vehicles for fuel and net hrs monitoring on 3rd May . portal linked by 5th May. | LIVE WEBSITE | Moba director requested CEO sir for meeting on 19th Mon / 20th Tue | once final demo completed contract and rate negotiation to start |  |  |  | #REF! | #REF!
FUEL DISPENSING | MOBA | HARSH / KARTICK | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | SARANGI SIR | 90% | ATG to be installed / final demo with MD sir | MOBA awaiting for date from mgmt when to come to KGp for final demo | Data fwded to Automobile head for inputs on 12th May . AUTOMATIC TANK GUAGING quoted for 3.42 lacs for two bowsers. Moba director requested for meeting on 19th Mon / 20th Tue | LIVE WEBSITE | Moba director requested CEO sir for meeting on 19th Mon / 20th Tue | once final demo completed contract and rate negotiation to start
VISUAL AI | THIRD EYE | ANIRBAN | SAFETY / PLANT | PROOF OF CONCEPT / PILOT |  | DIPANKAR SIR |  | Visit adani plant | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) Tata Mines ( Joda) ( Moisture quality inspection) Tata Iron ( JODA) - Safety Gear, Man Machine Interface IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) Adani - Odisha mines ( Wagon and Safety Gear) JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) Awaiting demo date | MSP Steel - ( Billet, Pillets, Conveyor, ANPR, Safety Gear) / Vedanta ( Jharsuguda ) - (Anode Crack Inspection & Safety Gear) / Tata Mines ( Joda) ( Moisture quality inspection) / Tata Iron ( JODA) - Safety Gear, Man Machine Interface / IOCL - Singroli ( Wagon Inspection, Safety Gear Inspection) / Adani - Odisha mines ( Wagon and Safety Gear) / JK Laxmi (Odisha)( Productivity, counting, Safety Gear, Speed Violation )( More than 1200+ Cameras across all these companies) / Road map and pricing shared | LINK |  | Dipanker jee will do demo on 20th may
ENGINEER DRAWING MANAGMENT SYSTEM | Multiple vendors | HITESH | PROJECTS | DISCOVERY PHASE |  | PATRA SIR |  |  |  | discovery call being done. some ppt received | LINK |  | Need to discuss with BU for selection of right software
PROCURE TO PAY | GEP | ARJUN | PURCHASE | CONTRACT NEGOTIATION & SIGNING |  | SANJAY SIR |  |  | CPO to meet GEP over zoom on 8th May 2 pm | Demo conducted with CPO on GEP for Procure-to-Pay process. /Integration meeting held with Ranabir Kar (SAP) to discuss implementation steps. GEP will be share the implementation plan by 23rd May. GEP will share the updated SOW 23rd May. | LINK |  | New agreement being drafted. MM module of SAP to remain active parallel to GEP
CRM | MS Dynamics | AMAN | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE |  | Target date required | MS dynamics team will provide demo on our data on 9th May | Quotation will be finalsed by 16th / 17th May | LINK
| Salesforce | AMAN | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE |  |  | Discovery meeting completed with new team. Salesforce has shared list oi partners with manufacturing experience . once partner finalized demo will be initiated | Customized demo with be provided on our data by Quadraforte (implementing partner) by 20th May | LINK | Anup Sir has advised not to go ahead with SF
| PIPEDRIVE | AMAN | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE | [5 empty] | Rejected by Mr George as the CRM did not supported workflow / approval mechanism
HRMS | Workday | AYUSH | HR | IMPLEMENTATION |  | CHAITANYA | 6% |  | Discussion with Anup jee and WD is completed on 1st May. awaiting feedback from WD | Email has been sent to workday to deffered payments by 90 days alignment with deloitte as per advised by Anup ji. | LINK | 15,200 USD is pending due for Training payments.
HRMS | Deloitte | AYUSH | HR | IMPLEMENTATION |  | CHAITANYA | 7% | Need ppt of data shared | Project planning and documentation completed by 20th Apr. Design phase for Core HCM and recruitment is in progress | Implemetation progress at 5% as per the whole project. we are on 7th week, work Progress is on track as per deloitte. PO shared with deloitteAs discussed with Delloite as agreed they will complete phase 1 - Core HR and recruitment module by Aug 25. | LINK
TMS Internal Shifting | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ | 99% |  |  | Tracker shared by logistic team |  |  | Few Reports related to MIS are pending to update im Fretron | 20.05.2025
TMS Outbound Movement | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ | 95% |  |  | Auction Module Live. |  |  | some new changes pending day by day for development.
[7 empty] | 57% |  |  | Tracking Tested, MIS reports are under development stage by Fretron |  |  | MIS reports and some SAP related task are under development of cancellation. | 05.06.2025
TMS Seamless / Bio Mass | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ | 100% |  |  | Maunal bidding initiated via Fretron TMS |  | These all are new Business requirements, so from Fretron Side Developers needs to present here to understand all the process at Site and give the Final target date for completion with proper understading is immediate required.
[7 empty] | 4% |  |  | BRD discussion is pending with concerned BU. Now based on SAP Integration data to be captured for Billing of Vendors. |  |  | SAP integration Pending with Fretron.
TMS Coal Movement | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ | 100% |  |  | Maunal Trip tracking and load utilisation started
[7 empty] | 21% |  |  | Integration discussion going with Technical team and SAP. |  |  | SAP integration Pending with Fretron.
[10 empty] | Billing of Vendor to be upload in Fretron as per trip for payment process. |  |  | PO data to be uploaded in Fretron portal
TMS EXIM | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ |  |  |  | Bidding process discussed i discussed with BU on 13.05.25 and Documents needed by Fretron from BU submitted by Pritamji on 14.05.25 |  |  | Fretron work going on for necessary updation in portal, so that Local Plant to Port Bidding can be started in initial phase then after Port to Port operation to be capatued further.
TMS SAND Movement | FRETRON | KARTICK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG / MANOJ |  |  |  | BRD discussion is pending with concerned Department.
SAFETY | SGS | HARISH | SAFETY | IMPLEMENTATION |  | RAJAT | 41% | Mail to be sent to SGS | Progress review as per agreement tracker done on 25th april. | As on date 15 man power has been deployed / From 1st May daily observation MIS made / Recording 40 observations per day / 788 observations made till 20th May out of which 66% Open out of 29% Observations severe. | LINK
EMPLOYEE TRANSPORT | REGO | ARIRTA | ADMIN | IMPLEMENTATION |  | ADMIN | 41% | Anu sir to meet REGO MD | real time utilization being maintained. List of issues from rego end being listed On call booking demo pending /QR based boarding demo pending On call Mar and apr bill process under audit as per REGO agreement tracker they are at 47% Vehicle wise manpower list to be shared by admin team | Anu Sir met REGO MD on 15th May . Also advised to share target plan for technology deployment. Rego has submitted march bills on 17th May amounting to Total 29.56L (23.83L Employee transport+5.73L For on call). Admin to process / Utilization being tracked / on call app demo today / rest technology not started | LINK | Many supporting data missing with the bills.
PAYROLL | Protivity | AYUSH | HR/FINANCE/ AUDIT | IMPLEMENTATION |  | CHAITANYA |  |  | 2 resources deployed at site / data transfer from RML side is complete / ready for onboarding from 12th May | 2 resources deployed at site / data transfer from RML side is complete /Agreement tracker to be reviewed / Implementation on track / Final UAT by 25th May | LINK | Complete knowledge transfer from adrenaline to protivity must be 100% before switching off adrenaline |  | 31st May Protivity going live
QUALITY BIOMASS | SGS | SHANMUKA | BIOMASS | IMPLEMENATION |  | SURAJ NAMAN | 87% |  | Progress review as per agreement tracker done on 25th april. | Agreement Tracker at 87% , As on date average 8 man power has been deployed for Biomass Quality. Detailed review of Agreement is pending. | Daily Reports |  | A review meeting to be done with SGS team and Business person to complete the agreement to 100%.
QUALITY BIOCHAR | SGS | SHANMUKA | BIOCHAR | CONTRACT NEGOTIATION & SIGNING |  | PRABHAT SIR |  |  |  | Not started | LINK
QUALITY DIP | SGS | REDDY | DIP | IMPLEMENATION |  | ABHISHEK SIR | 25% | Mail to be sent to SGS | Progress review as per agreement tracker done on 25th april. | As on date average 51 man power has been deployed for DIP Quality. Detailed review of Agreement has been be done on 20th May with SGS team. a warning mail to be issued on 21st May | Daily Reports |  |  | 10th June
LAPTOP AND DESKTOP MIS | DELL / MAC BOOK | ANIRBAN/SHUSHANTA | IT | DEPLOYEMENT |  | IT team |  |  | Will collate data from IT team and share report by today. basic webpage will be ready by 10th May | IT asset MIS received. Draft SLA and Escalation Matrix recieved from DELL and Mac Book vendor as advised by Anu Sir / SOP for issuance of Desktop and Laptops being drafted / IT Ticketing tool MIS developed to track issues / DELL Desktop - 40 stock , 143 issued = 183 / DELL Laptop - 5 stock , 144 issued , 1 lost , 50 ordered = 190 | LINK | DELL & MAC Book Vendor requested 60 days planning in advance for any requirement.

## 15th July.
ERP | PRODUCT COMPANY / SUPPLIER | RML SPOC | DEPTS INVOLVED | ERP STATUS | RAG | BUSINESS USER | TCKR | BU / USER | Ceo Sir Advise / Suggestion | Current Status - 28th July | Next Steps | SUPPORT REQUIRED | ISSUES | SUPPORTING DOCS | TARGET DATE | TEAM MEMBER TARGET | 1000 | dubey
MES (ON HOLD) | AVEVA / GE / SIEMENS | DUBEY / SHANMUKA/ KARTHIK / REDDY | SEAMLESS/DIP / PROJECTS | TECHNICAL & COMMERCIAL EVALUATION |  | PATRA SIR |  |  | Comparative with other Vendors. Target for 3 yrs is 15- 17 Cr / It is on hold and to be considered in next phase. | >Technical and commercial comparison of 3 vendors has been submitted to mgmt for review. GE quoted 19 Cr, AVEVA - 31 Cr and Siemens 29 Cr >Meanwhile mails has been sent to individual members for 15-16 Cr Budget for the next 3 yrs (5 Cr / yr) | >Technical and commercial comparison of 3 vendors has been submitted to mgmt for review. GE quoted 19 Cr, AVEVA - 31 Cr and Siemens 29 Cr >Meanwhile mails has been sent to individual members for 15-16 Cr Budget for the next 3 yrs (5 Cr / yr) |  | Quotations of vendor are on higher side , | LINK |  |  | 1200 | Anu sir
EPM | ORACLE | KARTHIK / HARSH | FINANCE / SAP / PWC | TECHNICAL & COMMERCIAL EVALUATION |  | ANUP SIR |  |  | Commercial comparision with SAP and Oracle | >Oracle EPM meeting was with CIO and DGM accounts. > Meeting to be scheduled on 27th July. | > Finance team and CIO to take final call for next steps. |  |  |  |  | Get questionnaire from Oracle and Discuss with CIO
TELEMATICS |  | KARTHIK / HARSH | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | ANURAG SIR & MANOJ SIR |  |  | First anurag to confirm then MD Sir | >Ignition on /off only available from MOBA sensor, Secondary engine data report available with machines having secondary engine like transit mixtures. No information of net hrs from Forklift or Hydra / Data to flow from MOBA to fretron for billing purpose >Finding alternate vendors , Blackbox is widely preferred by business users for its reliability and performance. >Revised SOW prepared by the Business Units (BUs), detailing all report types and specific modifications they require in the FMS Blackbox system. >Blackbox accepted the SOW, and demo phase will start soon. >Blackbox provided the following details as part of the evaluation process: -Their client list -Total number of licenses currently being managed -Company turnover | >Detailed implementation plan >The Proof of Concept (POC) is awaited from Blackbox, post which further steps will be finalized. >draft of the Payment Confirmation Purchase Order (PO) needs to be prepared. |  | Net working hrs is difficult to calculate with basic sensors in MOBA Stores is delaying to provide demo vehicles | LIVE WEBSITE |  | Meet all BUs and get the finalised SOW. Share it with Vendor and get approved . Need demo based on SOW
PLANNING & FORECASTING | BY /o9 | DUBEY / SHANMUKA/ KARTHIK / REDDY | PLANNING | TECHNICAL EVALUATION |  | PREM SIR |  |  | Comparative with other Vendors. | > Technical offers have been received from all vendors. > Commercial offer has been received only from O9. > Technical comparison has been completed for all three vendors. > As per the instructions from the CIO and PPC Head, the discussion with Blue Yonder is currently on hold due to their estimated cost of ₹16–20 crore for 3 years, which is significantly higher. | > The meeting will be scheduled as per the instruction of the PPC Head, since BY is offering a higher budget. > The technical and commercial comparison has already been completed and shared with the PPC Head ,CIO and relevant team members. |  | O9 quoted 18 Cr for 3ys (DIP+ seamless) | LINK |  | Meet CIO ,PPC head and discuss the next steps
PLANNING & FORECASTING | AVEVA | DUBEY / SHANMUKA | PLANNING | DICOVERY PHASE |  | PREM SIR |  |  |  | > The technical offer was received on 27th May, and AVEVA shared their revised technical offer on 18th July. > A technical meeting between AVEVA and RML was conducted on 16th June. > The commercial offer was received on 12th July, based on a SaaS model (including cloud pricing). > Implementation Charges (one-time, for Seamless and DIP Plants): ₹2.92 Crores > Annual Software \& License Cost (for DIP and Seamless Plants): ₹1.12 Crores per year > The meeting with our PPC Head is still pending from AVEVA's side due to a personal medical issue of their reporting manager, Mr. Sudhir Dembi. > As per the instruction of our CIO and PPC Head, I discussed the possibility of implementing the Planning module in SAP with Ranbir Sir. He had initiated an inquiry with PwC on 21st July, but unfortunately, there has been no response from PwC so far. | > The next step will begin once the PPC Head confirms to proceed with the negotiation with AVEVA |  |  | LINK
ENGINEER DRAWING MANAGMENT SYSTEM | Multiple vendors | DUBEY / HITESH | PROJECTS | DISCOVERY PHASE |  | PATRA SIR |  |  |  | > RFQ Sent To: Wrench, Bentley, Eisen Vault, GloboDocs, Ascetra, and SHAREDOCS (Hridayam Soft Solution) >Bentley: Accepted our Scope of Work (SOW). An internal technical discussion was held on 15th July, during which Bentley agreed to provide licenses for 25 users as per our requirements. Technical offer received on 23rd July. > Wrench: A technical discussion was held on 14th July with the business user (Design Head). Wrench shared the sub-features of their EDMS solution on 15th July. As per the instruction of the business user on 16th July, they submitted the revised technical Scope of Work (SOW) on 19th July, and have now submitted the commercial offer on 23rd July at 1 PM. > Eisen Vault: Ms. Avantika informed us on 12th July that their technical team was unable to attend the scheduled meeting due to unforeseen medical reasons. I followed up with her via email, and on 21st July, she again cited the same reason. However, on 24th July, she confirmed that the technical offer will be shared by 26th July. I followed up again, and she has now confirmed that the offer will be shared by 29th July. > GloboDocs: No response received yet on the RFQ. > Ascetra: Not capable of fulfilling the entire set of requirements; only partial compliance is possible from their side. > SHAREDOCS (Hridayam Soft Solution): An internal discussion was held on 21st July. They shared their mapping solution along with details of SHAREDOCS Enterprise capabilities. Techno-commercial offer received on 28th July. | A meeting is scheduled with Bentley on 29th July for commercial discussion based on the offer they have provided. Once we receive the techno-commercial offer from Eisen Vault, we will prepare the complete comparison sheet and share it with the Project Head and B.K. Rout Sir within one day. |  |  | LINK |  | follow up with BU to get queries solved , get commercials asap
PROCURE TO PAY | GEP | ARJUN / PRATEEK | PURCHASE | CONTRACT NEGOTIATION & SIGNING |  | SANJAY SIR |  |  |  | >Implementation to be done by GEP > MM module of SAP to remain active parallel to GEP. >RML to finalize the SOW > Legal team has raised comments on the Agreement sent by GEP; Legal head has confirmd the comments. >Based on commets Procurement team has revised the agreement. >CIO Sir has reviwed the agreement. >Order form has been revised according to the LOI Submitted by RML. >Shared the Updated SoW and Order Form and Master Service Agreement with GEP by RML | > The meeting between the Procurement Team and GEP to discuss the changes in the SOW/MSA has been scheduled for 30th July. > GEP is scheduled to visit RML in the first week of August. The final date will be confirmed based on the availability of the CEO and the management. |  |  | LINK | 10th Aug
MASTER DATA MANAGEMENT | Many Vendors | ARJUN / PRATEEK | PURCHASE | CONTRACT NEGOTIATION & SIGNING |  | SANJAY SIR |  |  |  | > SOW has been reviewed by CPO and sent to SAP team for review. > 6 companies (Pilog, Stridely Solutions,Hofincons,Prospecta,Cogniviti Labs,Exalca) have accepted the SOW and want to show the demo. > Pilog commercial recieved. > Prospecta showed DEMO to MDM team. >CPO sir changed the requirment .Whole project will be outsource(MANPOWER+ SOFTWARE) >Revised SOW has been sent to all the vendors >Received the techno-commercial offer from Stridely, prospecta and pilog, Cogniviti Labs, Exalca > Stridely DEMO with CIO and Procurement team > All the received offers have been sent to SAP (ranabir sir) for review | >commercial yet to be recieved for bluespring >Demo is pending for Exalca and bluespring >New software release and sign off by CPO. >Commercial will be recieved by 15th july. | > SAP team review the SOW | Material and vendor master being cleaned of duplicate values- 65k rows | LINK |  | All demo to complete and need commercials from all vendors asap. make comparative of SOW and quotation on 11th July.
CRM | MS Dynamics | Hitesh/Harish | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE |  | CHRO / CIO / Planning Head / Export Head |  | > Quotation received.(Total = 1.4cr approx.) License cost - 76.9 Lakh/year Implementation cost - 68.5 Lakh Onsite support of 200 person hrs/1 year - 4.5Lakh | >Comparitive has been prepared and forwarded to CHRO. > CIO and CHRO has selected SalesForce. | Awaiting Management decision. |  | LINK |  | Make a technical comparative of SALESFORCE and MS dynamics from web data
CRM | Salesforce | Hitesh/Harish | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE |  | CHRO / CIO / Planning Head / Export Head |  | > Final Quotation received from SF and Implementing Partner .(Total is same = 1.2cr approx.) >License cost - increased from 46.2 Lakh/year to 52.6 Lakh/year (Mobile Publisher for Employees and Members 141 users) >Implementation cost - decreased from 78 Lakh to 67 Lakh >Onsite support per month - 3.5Lakh (same) >CIO, CHRO, Salesforce ad IP had a joint dicussion for price negotiation >CHRO has aldready met Implementing Partner in Dubai. | >Target price as advised by management is 70-80 Lakhs | Awaiting Management decision. | > Implementing Partner need to accept UAT based payment terms or advanced payment against BG to RML. >OEM to give credit according to UAT of implementing partner or link the first year subscription fees with Implementing Partner payment terms. | LINK
HRMS | Workday | AYUSH / SHARIQUE | HR | IMPLEMENTATION |  | CHAITANYA | 9% |  | Send a strong mail to defer the payment timelines or to end partnership | >An email has been sent to Workday to defer payments by 90 days alignment with Deloitte, as advised by Anup Ji / George. Workday rejected the request. Strong mail again sent to Work Day. On 23rd CIO, CHRO had meeting with WD APAC leadership. | >WD to revise and come back on acceptence of payment terms |  |  | LINK |  | Need to discuss with CIO.
HRMS | Deloitte | AYUSH/SHARIQUE | HR | IMPLEMENTATION |  | CHAITANYA | 9% |  | Need ppt of dashbord | >Current Status: >Phase 2 design sessions have been completed. >Phase 2 has modules, namely Compensation, Learning, Performance, Talent Management, and Expenses modules. >Deloitte has asked RML for the workbook data for the design sessions of Phase 2. >RML needs to sign off on the Gold Build to go live for Phase 1. >Testing of the HCM and Recruitment Modules has been completed at 100%. >Production data, updated cost centers, inactive employee data, and new cost center hierarchy data for Phase 2 have been shared with Deloitte. | >Phase 1 will go live by the end of July. | > Additional manpower is required. |  | LINK |  | Revise the payment schedule. Get update from sushant , Chaitanya all BU invidually as well as Workday. and merge . Get the portal tested . Implementation tracker update
FDMS | MOBA | HARSH / KARTHIK | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | SARANGI SIR , ANURAG SIR & MANOJ SIR | 90% |  | ATG to be installed / final demo with MD sir | > The data was forwarded to the Automobile Head for inputs on 12th May. The quotation for the Automatic Tank Gauging system is ₹3.42 lakhs for two dispensers. > Anurag Ji and the Automobile Head have confirmed the successful functioning of the software and the completion of User Acceptance Testing (UAT). >Blackbox can perform both FDMS AND FMS | >ATG to be included and price negotiation to start, Since MOBA FMS is not as as per Sir requirement , we are evaluating other companies with FDMS and Net hrs (FMS) capabilities >Demo date needs to be finalized after final decision. |  | MOBA FLEET MGMT SYSTEM has not met CEO sir requirement | LIVE WEBSITE
TMS INBOUND | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 100% | Manoj Ji / Anurag Ji |  | >Inbound is completed and live |  |  |  | LINK |  | Comparative of issues from RML and fretron. get summary of quotation for other modules
TMS OUTBOUND | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 75% | Manoj Ji / Anurag Ji |  | From SAP side all cancellation related task are completed but Multiple DO selection or multiple SO selection along with advanced Billing process is pending which is to be done by SAP team. Also some PO related task is pending . Meeting was conducted with CIO on 11th July. Fretron shared pending issues mail and pending for discussion from RML Side. Fretron team discussing with SAP team to complete the pending tasks. | SAP Side confirmation is pending. Clarification for all tasks related to SAP is awaited from SAP team. | SAP Support. | BU has stopped payment of 12 lakhs since outbound dashboard is not complete. | LINK
TMS SEAMLESS | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 4% | Manoj Ji / Anurag Ji |  | Manual bidding has been initiated via Fretron in Seamless. BRD aldready completed, Commercial recevied from Fretron. | Final commercial Approval for the project from management is pending | The SAP integration component remains pending from the SAP side since it is a new requirement. |  | LINK
TMS BIOMASS | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 4% | Manoj Ji / Anurag Ji |  | BRD aldready completed, Commercial recevied from Fretron . | Final commercial Approval for the project from management is pending | The SAP integration component remains pending from the SAP side since it is a new requirement. |  | LINK
TMS SAND MOVEMENT | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 0% | Manoj Ji / Anurag Ji |  | BRD aldready completed, Commercial recevied from Fretron . | Final commercial Approval for the project from management is pending | The SAP integration component remains pending from the SAP side since it is a new requirement. |  | LINK
TMS COAL MOVEMENT | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 21% | Manoj Ji / Anurag Ji |  | BRD aldready completed, Commercial recevied from Fretron . | Final commercial Approval for the project from management is pending | The SAP integration component remains pending from the SAP side since it is a new requirement. |  | LINK
TMS EXIM | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | 0% | Manoj Ji / Anurag Ji |  | All requirements have been provided to Fretron by the PPC head and their team. Additionally, the Fretron team has conducted a demo related to EXIM to Logistics team. Fretron has given demo of EXIM bidding. EXIM process has strted in Bahrain partially. | Complete BRD to be dicussed from Fretron and Commercial to be recieved. | The SAP integration component remains pending from the SAP side since it is a new requirement. |  | LINK
CONTRACT LABOUR AND COMPLIANCE OUTSOURCE | EMPSHERE | ARJUN / HARSH | RML1 & 6(DIP)/BIO MASS/ISP/PRE-CAST/FITTING/SEAMLESS/NITRILE/LATEX | CONTRACT NEGOTIATION & SIGNING |  | ANU SIR |  |  | Immediate sign off thru Business user. Agreement to be drafted | Price negotiated as Rs 12.76 lac per month for 5000 labourers. Meeting with Anu Sir and emsphere implementation team is complete. SOW has been finalized and briefed to Anu Sir. Implementation plan shared by Emsphere. Reference check / Plant visit can be done >Agreement redrafted with new SOW, payment terms. > CIO solved IT related clause in Agreement of CLMS >RACI Matrix recieved from EMSPHERE and shared with CIO. >Emsphere has split the agreement into two agreements — one for software-related services and the other for the manpower they are providing. Both agreements have been shared by Emsphere. >Both the manpower-related and software-related agreements have been shared with the legal team for review. | > RML will review the changes made by Emsphere in the agreement, after which further steps will be taken. | > Need a meeting with management to finalize and sign off agreeement. |  | LINK | 31st July | Arrange meeting with CIO, ERPteam and empshere immediately |  | 2490000 | 8545200 | 13248000
EMPLOYEE TRANSPORT | REGO | ARITRA | ADMIN | IMPLEMENTATION |  | ADMIN | 52% |  | > App is in testing phase. CIO sir give time till 31st July for Full technical implementation. > He instructed to install GPS in all the vehicles including Back-up ones. | 1. Payment released of ~22.48 Lakhs (ETS) and ~5.73 Lakhs (On-Call) for the month of March. 2. Payment released of ~34.21 Lakhs (ETS) and ~2.06 Lakhs (On-Call) for the month of April. 3. Payment released of ~5.4 Lakhs (On-Call) for the month of May. 4. May ETS Bill of ~53.1 Lakhs submitted / ~38.4 Lakhs payable acc. to SGS. 5. June ETS Bill of ~52.3 Lakhs submitted. 6. GPS installed in all vehicles (except one traveller- WB23J2391). 7. On-call booking & invoicing is done through web-portal. But no proper ans given by Rego for Huge KM difference from the actual route distance. 8. ETS app to be rolled out for all employees very soon. 9. Website for utilization and finance tracking is live. Admin utilise this interactive dashboard for optimization. | 1. Meeting to be done with Admin Team, Rego Team regarding agreement revision. 2. App will be roll out soon to all employees. |  | 1. Back-up vehicles conditions are too bad. 2. New vehicles are Out of Service for 1-1.5 months. 3. No proper maintenance is done. 4. Agreement is still at 58 even after 4.5 months. | LINK |  | Aritra to update sheet till july . REGO dashboard to be updated
PAYROLL | Protivity | AYUSH | HR/FINANCE/ AUDIT | IMPLEMENTATION |  | CHAITANYA | 85% |  |  | >Implementation progress stands at 85%. >Final UAT Sign off is still pending. >No time line is provided on ATS from protiviti side >Loan and Advance Modules has been implemented and shown to Chandan Modi sir. >Onboarding alerts : require task assignment to stakeholders with a deadline of 29th July >Exit Module: Date submission freeze, Hierarchy bypass (Already in discussion with GreytHR and possibility to get revert on the solution by 25-Jul-2025) >Payroll: Turms not completely Implemented (90% Completed) >OT Assignment is pending to be implemented. >Geo Tracking is has been implemented and in use. >AR Excel Download : Implementation Done yet. >Probation Completion: Form under configuration | >Asset Management is working but new requirement are coming from RML Side to configure >Daily Boarding & Exit Reporting : Pending >Offer Pending for Approval Template : Pending >Dashboards for HR, BU, CEO Cell : Pending >Recruitment and Hiring Report, Template has already been shared; Abhishek will revert with the timeline. >Promotion and Internal Movement Report, Template has already been shared; Abhishek will revert with the timeline. |  |  | LINK |  | Talk to individual BU and vendors and get update. Check portal and update the agreement tracker. Modules activated or not. Identify the Pain points targets. Agreement tracker to updated.
CONTAINER TRACKING | VILLIOT | KARTHIK | LOGISTICS | CONTRACT NEGOTIATION & SIGNING |  | RREL |  |  |  | >Revised SLA and agreement shared by Villiot. > CIO had a meeting with BU where queries were raised on 3rd July. >The CIO met Harish, and Harish followed up with an email to the CIO, sharing the vendor-provided solutions to the technical queries raised. > CIO sir approved and signed physically on SLA and agreement. > Recieved a mail from Harish Sir with signed and stamp on SLA informed to CIO Sir., Harish sent signed copy from vendor.Awaiting for payment approval from Management. | Sign off and release of payments . Harish Sir will be sending signed agreement by 15th July |  | > No warranties or SLA given by Villiot. RREL is taking technical responsibility of Partner . >75% balance payment – Container Tracking | LINK |  | Follow up Cio for next steps.
SECURITY SURVEILLANCE | Saminfo Technologies | HITESH | SECUIRTY AND ADMIN | CONTRACT NEGOTIATION & SIGNING |  | DIPANKAR G |  | Dipankar Ji. |  | >Dipankar Sir and CIO had a joint discussion on Scope and Outcomes on 2nd July. >Vendor gave the demo on 2nd July. | >Contract agreement to be drafted . | > Price comparitive from other vendors required. | BOM quantity not fixed, rate to be negotiated, software to be developed, no. of man power not defined | LINK
LAPTOP AND DESKTOP MIS | DELL / MAC BOOK | HITESH | IT | DEPLOYEMENT |  | IT team |  |  |  | IT asset MIS received. Draft SLA and Escalation Matrix recieved from DELL and Mac Book vendor as advised by Anu Sir / SOP for issuance of Desktop and Laptops being drafted / IT Ticketing tool MIS developed to track issues / DELL Desktop - 40 stock , 143 issued = 183 / DELL Laptop - 5 stock , 144 issued , 1 lost , 50 ordered = 190 Total desktop- 585 issued-525 rental-184 stock- 60 |  |  | DELL & MAC Book Vendor requested 60 days planning in advance for any requirement. | LINK
QUALITY BIOMASS | SGS | SHANMUKA / REDDY | BIOMASS | IMPLEMENATION |  | SURAJ NAMAN | 87% |  |  | >Agreement Tracker at 87% , As on date average 8 man power has been deployed for Biomass Quality. | Next review to be done by 29th July. | Bio mass Plant shutdown |  | Daily Reports |  | Review meeting on 3rd July. Dashboard to be created
QUALITY DIP | SGS | REDDY/HARISH | DIP | IMPLEMENATION |  | ABHISHEK SIR | 68% |  | Mail to be sent to SGS | >Agreement Tracker at 68% , As on date average 96 man power has been deployed for DIP Quality. >Detailed review of Agreement has been be done on 25th May with SGS team. >currently only 3 lines are running in rml-1&6 | Next review to be done by 29th July. |  |  | Daily Reports |  | Review meeting on 3rd July . Dashboard to be created
SAFETY | SGS | HARISH/ REDDY | SAFETY | IMPLEMENTATION |  | RAJAT | 46% |  | Mail to be sent to SGS | >As on date 17 man power has been deployed >From 1st May daily observation MIS made >Recording avg 38 observations per day >3335 observations made till 26th July out of which 17% Open. >13% of all Open Observations are SEVERE. >Internal review completed between BU and vendor where Progress increased from 46% to 50% >Safety attendance dashboard outline done >Safety MT attendance Front End configuration done. >Individual Employee model has been deployed. | > Safety head will join from first week of august. | Safety head offer letter has been sent and will be joined by 23rd July. |  | LINK |  | OBs MIS to be updated. Critical issues to be make seoerate list need to be mailed to BUs Safety update till 6th July.
[19 empty] | 0 | 0
IT Asset | CSI / Computer Junction / Lenovo | HARISH/ REDDY | SAFETY | IMPLEMENTATION |  | RAJAT |  |  |  | CJ:- Macbook > May Payement done; PO: 5400032129; Amount: 1,02,500 > June Payement Pending; Putup on 14th July > 10 laptop need to return( vendor sent without PO ) > Payment terms: 4100/Macbook( monthly) ; post payment; CSI:- Dell > 140 laptop + 128 desktop payment done till September. > 55 desktop payment pending: Invoice not received from vendor. > payment advance > 1525/laptop/month ( quaterly) > 1468/desktop/month (quaterly) NVC:- Lenovo > 60 laptops received. > Payment not done( No invoice ). > Payment terms: Post Payment; > 2490/laptop/month ( quaterly ) > New requirement : 2 high performance laptops | > CJ payment issues to be dicussed with CIO and CIO need to sign to release payment . > IT Asset - Dash board to be prepared > IT Ticketing tool to be used by all employees > IT asset application flowchart will be completed by 4th July > IT Asset Demo to be given on 9th July |  | >Computer Junctn demanding 2 months rent | LINK |  | Next step based targets
CCTV | [8 empty] | New Project | Research and comprehensive analysis to identify the top 3 CCTV camera manufacturing companies, categorizing the various types of cameras they produce, detailing their specific applications and use-cases, and mapping each camera type to its respective HSN code Analyzing security systems across home, industrial, and public sectors. Identifying technologies, materials, and deployment methods in each domain. Conducting a thorough research to create a detailed sheet of all camera types manufactured in India, including current values, images, and VOLZA-based import-export data. Analyzed whether companies import parts or complete cameras, with clear insights on volume and sourcing and fiinding each part HSN code through VOLZA PLATFORM Identify all machinery essential for CCTV manufacturing and their potential suppliers. Research how IP cameras and PTZ network cameras work, their parts, and how they function in detail. Study SOS startups — how they work, how they develop and make chips in their own company. | Make a full explanation of IP/PTZ CCTV cameras, step by step, how each part works and how they function overall. Understand STQC law by the Indian government and how companies are still importing despite this law. Find out what equivalent testing/certifications are used in US, UK, and other countries for CCTV cameras
SAP ASSESSMENT | [7 empty] | CIO / SAP Head |  | >received SAP assessment proposal PPT from Protiviti. > Identified KPMG and Deloitte as an alternative vendor for the assessment. > CIO sir has recommended another company(Infobiz) and he will look forward in it. | It is being handled by CIO sir |  | Protivity is not replying |  |  | Get confirmation from CPO and CIO to know which partntner to be selected. Solve issues from KPMG and Deloitte as recomended by CPO Sir.

## HP
ERP | PRODUCT COMPANY / SUPPLIER | RML SPOC | DEPTS INVOLVED | ERP STATUS | RAG | BUSINESS USER | BU / USER | Current Status - 24th June | Next Steps | SUPPORT REQUIRED | ISSUES | SUPPORTING DOCS | TCKR % | TARGET
CRM | MS Dynamics | Hitesh/Harish | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE | CHRO / CIO / Planning Head / Export Head | > Quotation received.(Total = 1.4cr approx.) License cost - 76.9 Lakh/year Implementation cost - 68.5 Lakh Onsite support of 200 person hrs/1 year - 4.5Lakh | >Comparitive has been prepared and forwarded to CHRO. > CIO and CHRO has selected SalesForce. |  |  | LINK
CRM | Salesforce | Hitesh/Harish | SALES - ALL DEPTS | TECHNICAL EVALUATION |  | MR GEORGE | CHRO / CIO / Planning Head / Export Head | > Final Quotation received from SF and Implementing Partner .(Total is same = 1.2cr approx.) License cost - increased from 46.2 Lakh/year to 52.6 Lakh/year (Mobile Publisher for Employees and Members 141 users) Implementation cost - decreased from 78 Lakh to 67 Lakh Onsite support per month - 3.5Lakh (same) >CIO, CHRO, Salesforce ad IP had a joint dicussion for price negotiation >CHRO has aldready met Implementing Partner in Dubai. | >Target price as advised by management is 70-80 Lakhs | >Re nogotiate to happen with CIO and CHRO. | > Implementing Partner need to accept UAT based payment terms or advanced payment against BG to RML. >OEM to give credit according to UAT of implementing partner or link the first year subscription fees with Implementing Partner payment terms. | LINK |  | 15th June 23rd June 30th June
CONTRACT LABOUR AND COMPLIANCE OUTSOURCE | EMPSHERE | ARJUN / HARSH | RML1 & 6(DIP)/BIO MASS/ISP/PRE-CAST/FITTING/SEAMLESS/NITRILE/LATEX | CONTRACT NEGOTIATION & SIGNING |  | ANU SIR | ANU SIR | Price negotiated as Rs 12.76 lac per month for 5000 labourers. Meeting with Anu Sir and emsphere implementation team is complete. SOW has been finalized and briefed to Anu Sir. Implementation plan shared by Emsphere. Reference check / Plant visit can be done | Agreement to be redrafted with new SOW, payment terms. |  |  | LINK |  | ACT 31ST MAY / REV - 10TH JUN / 15TH JUNE 30th June
MASTER DATA MANAGEMENT | Many Vendors | ARJUN / PRATEEK | PURCHASE | CONTRACT NEGOTIATION & SIGNING |  | SANJAY SIR | CPO | > SOW has been reviewed by CPO and sent to SAP team for review. > 3 companies have accepted the SOW and want to show the demo. | Demo and commercial yet to be recieved. New software release and sign off by CPO. |  | Material and vendor master being cleaned of duplicate values- 65k rows | LINK |  | 15th June 25th June
HRMS | Workday | AYUSH / SHARIQUE | HR | IMPLEMENTATION |  | CHAITANYA | HR | An email has been sent to Workday to defer payments by 90 days alignment with Deloitte, as advised by Anup Ji / George. Workday rejected the request. Strong mail again sent to Work Day. On 23rd CIO, CHRO had meeting with WD APAC leadership. | WD to revise and come back on acceptence of payment terms |  |  | LINK | 9%
HRMS | Deloitte | AYUSH/SHARIQUE | HR | IMPLEMENTATION |  | CHAITANYA | HR | Implemetation progress at 9% as per the whole project. PO shared with deloitte. As confirmed by Delloite, they will complete phase 1 - Core HR and recruitment module by Aug 25. Resource onboarding of phase 2 has been started. | The Testing of Recruitment Module and HCM module has been started on June 11. Testing of the these 2 modules will conclude by 26th june. |  | Employee location mapping needs to be done in workday | LINK | 9% | 30th Aug
TMS INBOUND | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | Audit team should confirm the weather the Billing report format is satisfied or not. Trigger alert for Digital contracts pending from Fretron. | Fretron is expected to complete the remaining pending tasks related to internal movement at the earliest. |  |  | LINK | 99% | 20.06.2025
TMS OUTBOUND | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | From SAP side all cancellation related task are completed but Multiple DO selection or multiple SO selection process is pending which is to be done by SAP team by 20th June. Also some PO related task is pending . Awaiting for report from Fretron given by Buisness user. | TMS UAT is to be scheduled by 20th June |  | BU has stopped payment of 12 lakhs since outbound dashboard is not complete. | LINK | 63% | 25.06.2025
TMS SEAMLESS | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | Manual bidding has been initiated via Fretron in Seamless. The BRD discussion has been completed. | BRD shared by Fretron for final approval from BUs based on it commercial will be shared. | The SAP integration component remains pending from the SAP side since it is a new requirement. | No response on quoatation from Fretron after we have shared BRD | LINK | 4% | 25.06.2025
TMS BIOMASS | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | The BRD discussion has been completed. | BRD shared by Fretron for final approval from BUs based on it commercial will be shared. | The SAP integration component remains pending from the SAP side since it is a new requirement. | No response on quoatation from Fretron after we have shared BRD | LINK | 4% | 25.06.2025
TMS SAND MOVEMENT | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | The BRD discussion has been completed. BU informed sand movemet process is stopped, until new tendor comes it wont start. | BRD shared by Fretron for final approval from BUs based on it commercial will be shared. | The SAP integration component remains pending from the SAP side since it is a new requirement. | No response on quoatation from Fretron after we have shared BRD | LINK | 21% | 25.06.2025
TMS COAL MOVEMENT | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | The BRD discussion has been completed. | BRD shared by Fretron for final approval from BUs based on it commercial will be shared. | The SAP integration component remains pending from the SAP side since it is a new requirement. | No response on quoatation from Fretron after we have shared BRD | LINK | 21% | 25.06.2025
TMS EXIM | FRETRON | KARTHIK | LOGISTICS / EXIM | IMPLEMENTATION |  | ANURAG SIR & MANOJ SIR | Manoj jee / Anurag jee | All requirements have been provided to Fretron by the PPC head and their team. Additionally, the Fretron team has conducted a demo related to EXIM to Logistics team. Now BUs inform fretron to start with bidding first so that remaing upcoming processes to be done later. | Commercial to be shared by Fretron. | The SAP integration component remains pending from the SAP side since it is a new requirement. | No response on quoatation from Fretron after we have shared BRD | LINK | 0% | 25.06.2025
PROCURE TO PAY | GEP | ARJUN / PRATEEK | PURCHASE | CONTRACT NEGOTIATION & SIGNING |  | SANJAY SIR | CPO | >Implementation to be done by GEP > MM module of SAP to remain active parallel to GEP. >RML to finalize the SOW > Legal team has raised comments on the Agreement sent by GEP; awaiting confirmation from the Legal Head. | Agreement from RML to be drafted based on SOW. CPO and CIO to finalize the next steps. |  | Material and vendor master being cleaned of duplicate values- 65k rows | LINK |  | 15th June 25th June
CONTAINER TRACKING | VILLIOT | KARTHIK | LOGISTICS | CONTRACT NEGOTIATION & SIGNING |  | RREL | RREL / CPO | >Revised SAL and agreement shared by Villiot. > CIO had a meeting with BU where queries were resolved > CIO need to meet the vendor, BU to arrrange the meeting | Sign off and release of payments . Meeting of RREL with CIO and vendor. |  | > No warranties or SLA given by Villiot. RREL is taking technical responsibility of Partner . >75% balance payment – Container Tracking | LINK |  | 10th June / 16th June

## LP
ERP | PRODUCT COMPANY / SUPPLIER | RML SPOC | DEPTS INVOLVED | ERP STATUS | RAG | BUSINESS USER | TCKR | BU / USER | PRIORITY | Current Status - 24th June | Next Steps | SUPPORT REQUIRED | ISSUES | SUPPORTING DOCS | TARGET
MES | AVEVA / GE / SIEMENS | DUBEY / SHANMUKA/ KARTHIK / REDDY | SEAMLESS/DIP / PROJECTS | TECHNICAL & COMMERCIAL EVALUATION |  | PATRA SIR |  |  |  | >Technical and commercial comparison of 3 vendors has been submitted to mgmt for review. GE quoted 19 Cr, AVEVA - 31 Cr and Siemens 29 Cr >Meanwhile mails has been sent to individual members for 15-16 Cr Budget for the next 3 yrs (5 Cr / yr) | >All the vendors want to meet the business users for further technical and commercial negotiations. |  | Quotations of vendor are on higher side , | LINK | 10th June / 20th June
ERP | ORACLE | KARTHIK / HARSH | FINANCE / SAP / PWC | TECHNICAL & COMMERCIAL EVALUATION |  | ANUP SIR |  |  |  | >CIO will do a SAP assessment of RML to understand the status of SAP and need for Oracle
TELEMATICS | MOBA | KARTHIK / HARSH | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | ANURAG SIR & MANOJ SIR |  |  |  | Ignition on /off only available from MOBA sensor, Secondary engine data report available with machines having secondary engine like transit mixtures. No information of net hrs from Forklift or Hydra / Data to flow from MOBA to fretron for billing purpose Finding alternate vendors , 4 accepted our SOW, Discovery meeting in progress | >Demo have been arranged with new vendors who have accepted our sow >New vendors to be finalized with same FMS scope. >Selected vendors will give demo for net hrs and billing | New vendors to be finalized with same FMS scope. | Net working hrs is difficult to calculate with basic sensors | LIVE WEBSITE
TELEMATICS | NEW VENDORS | HARSH | AUTOMOBILE / LOGISTICS | DISCOVERY PHASE |  | ANURAG SIR & MANOJ SIR |  |  |  | Companies- (NYGGS, Black Box, Sahaj GPS, Tracknovate) being evaluated for final demo and POC. > Blackbox is widely preferred by business users for its reliability and performance. | A comprehensive consolidated document is to be prepared by the Business Units (BUs), detailing all report types and specific modifications they require in the FMS Blackbox system. Meeting to be scheduled between AGM Logistics and CIO awaitng CIO Sir approval | BU-Wise Consolidated Requirement Document |  |  | 22th June
PLANNING & FORECASTING | BY /o9 | DUBEY / SHANMUKA/ KARTHIK / REDDY | PLANNING | TECHNICAL EVALUATION |  | PREM SIR |  |  |  | > Technical offer received from all the vendors > Commercial is only received from O9 > Technical comparison is made between all 3 > BY will provide Commercial by 16th june | >BY/O9 - Commercial comparative to be made after all offers revieved. >Meeting of PPC head with Deliotte internal meeting on 16.06.2025. |  | O9 quoted 18 Cr for 3ys (DIP+ seamless) | LINK
PLANNING & FORECASTING | AVEVA | DUBEY / SHANMUKA | PLANNING | DICOVERY PHASE |  | PREM SIR |  |  |  | >Technical offer received on 27th May. >Technical Meeting with AVEVA and RML on 16th june. |  |  |  | LINK
ENGINEER DRAWING MANAGMENT SYSTEM | Multiple vendors | DUBEY / HITESH | PROJECTS | DISCOVERY PHASE |  | PATRA SIR |  |  |  | >AUTODESK, WRENCH, BENTLEY, GLOBODOX, EISHENVAULT, AVEVA, and SHAREDOCS > Meeting with Bentley completed, all queries were solved by Design & Maint. head | All the meetings with other vendors have been postponed and Design & Maint. head need to solve the queries sent by vendors | Design team. |  | LINK | 20th June / 25th June
FDMS | MOBA | HARSH / KARTHIK | AUTOMOBILE / LOGISTICS | TECHNICAL EVALUATION |  | SARANGI SIR , ANURAG SIR & MANOJ SIR | 90% |  |  | > The data was forwarded to the Automobile Head for inputs on 12th May. The quotation for the Automatic Tank Gauging system is ₹3.42 lakhs for two dispensers. > Anurag Ji and the Automobile Head have confirmed the successful functioning of the software and the completion of User Acceptance Testing (UAT). | ATG to be included and price negotiation to start, Since MOBA FMS is not as as per Sir requirement , we are evaluating other companies with FDMS and Net hrs (FMS) capabilities |  | MOBA FLEET MGMT SYSTEM has not met CEO sir requirement | LIVE WEBSITE
SECURITY SURVEILLANCE | Saminfo Technologies | HITESH | SECUIRTY AND ADMIN | CONTRACT NEGOTIATION & SIGNING |  | DIPANKAR G |  |  |  | >Dipankar Sir and CIO had a joint discussion on Scope and Outcomes. >CIO need to meet the vendor and BU to arrange the meeting | Meeting to be scheduled with CIO and Vendor for price negotiation on 23rd or 24th June |  | BOM quantity not fixed, rate to be negotiated, software to be developed, no of man power not defined | LINK

## OUTSOURCE
ERP | PRODUCT COMPANY / SUPPLIER | RML SPOC | DEPTS INVOLVED | ERP STATUS | RAG | BUSINESS USER | TCKR | BU / USER | PRIORITY | Current Status - 24th June | Next Steps | SUPPORT REQUIRED | ISSUES | SUPPORTING DOCS | TARGET
EMPLOYEE TRANSPORT | REGO | ARITRA | ADMIN | IMPLEMENTATION |  | ADMIN | 48% |  |  | > Payment released for March and Apr. > No technical roadmap given by vendor. > Meeting of Rego Technical person and CIO has been fixed for 25th June | > Technical person to be deputed at RML premises by REGO, for customization and demonstration. |  | > Back-up vehicles conditions are too bad. > New vehicles are Out of Service for 1-1.5 months. > No proper maintainance is done. > Agreement is still at 48% | LINK | ACT 31ST MAY / REV - 10TH JUN / 16TH JUNE REV - 23rd June
PAYROLL | Protivity | AYUSH | HR/FINANCE/ AUDIT | IMPLEMENTATION |  | CHAITANYA | 27% |  |  | >Implementation progress stands at 27%. >Final UAT Sign off is still pending. >Demo session of the employee ATS portal has been conducted. >GREYTHR ATS portal cost Rs 1800 per login >ATS tracker will be implemented in 10 days, Data Collection from HR has began | >Updation of SOW Tracker from Protivity, after the payroll of june has been done >HR to allot dedicated manpower > OT Module, Recruitment module and Loan and advancements module to be made live by next week. |  |  | LINK | 31st May 25th June
QUALITY BIOMASS | SGS | SHANMUKA / REDDY | BIOMASS | IMPLEMENATION |  | SURAJ NAMAN | 87% |  |  | >Agreement Tracker at 87% , As on date average 8 man power has been deployed for Biomass Quality. | Next review to be done in 4th week of June. |  |  | Daily Reports | 23rd June
QUALITY DIP | SGS | REDDY/HARISH | DIP | IMPLEMENATION |  | ABHISHEK SIR | 68% |  |  | >Agreement Tracker at 68% , As on date average 77 man power has been deployed for DIP Quality. >Detailed review of Agreement has been be done on 25th May with SGS team. |  |  |  | Daily Reports | 25th june
SAFETY | SGS | HARISH/ REDDY | SAFETY | IMPLEMENTATION |  | RAJAT | 46% |  |  | >As on date 14 man power has been deployed >From 1st May daily observation MIS made >Recording 40 observations per day >2090 observations made till 21st June out of which 19% Open. >30% of all Open Observations are SEVERE. >2nd week review completed between BU and vendor where Progress increased from 42% to 46%. | > SGS will send revised agreeent tracker > Review on 25th June | New safety head will join possibly after 25th june |  | LINK | 31st May 30th june
IT Asset | CSI / Computer Junction / Lenovo | HARISH/ REDDY | SAFETY | IMPLEMENTATION |  | RAJAT |  |  |  | > 10 laptops have been delivered by Computer Junction > Dell order has been released for 55 laptops. Awaiting delivery timeline from CSI/Dell > Lenevo team along with Rental partner will meet CIO on 25th June | > IT Asset - Dash board to be prepared > IT Ticketing tool to be used by all employees |  |  | LINK