## Sheet1
Modules that are yet to be implemented | Current Status | Remarks | Latest Remarks | Initial Deadline | New Deadline
Travel Advance | Pending | Domestic approval flow has been enabled for all users; it’s only pending for global employees. We have made a slight change in the requirement and need it updated accordingly. | For all global users, please add Mr. George as the final approver. Requirement was shared on 28th July 2025. |  | No Deadline has been provided yet
CEO Sirs Dashboard | Pending |  | Its implementation be done after all the modules of ESS portal has been Implemented |  | No Deadline has been provided yet
Application Tracking System | Pending | Sushanta's Comment : Have discussion with Chaitanya Sir, If Excel is possible to upload we can proceed with the same. For better clarity we can have a discussion and get it closed | RML has to confirm the same. |  | No Deadline has been provided yet
Employee Pulse Survey | Pending |  |  |  | No Deadline has been provided yet
Overtime Module | Pending | OT assigning to new employee is not done |  |  | No Deadline has been provided yet
Probation Completion | Pending | Form under configuration |  | 2025-07-29 | 2025-07-31
Asset Management & Location Tracking | Pending | Sushanta Comment :Yet to Implement, (Mr. Susanta Roy) sent today(24/07/2025) |  |  | 2025-07-29
Onboarding alerts To stakeholders | Pending | Tasks to be allocated to different stake holders and they have to perform tasks in accorance |  | 2025-07-29 | 2025-07-31
Earned Leave | Pending | Allocation of earned leaves to employees who have completed 1 year of service |  | 2025-07-31 | 2025-07-31
Partially implemented & Other Issues | Current Status | Remarks |  | Initial Deadline | New Deadline
Exit Management | Pending | Date submission freezed, Hirerchy bipass (Already in discussion with GreytHR and possibility to get revert on the solution by 25-Jul-2025) |  |  | 2025-07-30
Overtime Module | Pending | Sushanta's Comment : All OT must be informed to the reporting Manager on a daily basis.Managers must approve/reject OT within 48 hours of intimation.If not approved within 48 hours, it will not be considered as valid OT. |  |  | 2025-08-01
Payslip to be updated in line with the old | Pending | Payslip showcased and RML (Sushanta Nayak) in agreement - the values to be populated and showcased |  | 2025-07-29 | On the meet occured on 29th of july, Protiviti said it would be implemented by tonight
Reports to be configured in the System | Current Status | Remarks |  | Initial Deadline | New Deadline
Offer Pending for Approval Template | Pending | Abhishek to share the already availble report for checking |  | 2025-07-25 | No Deadline has been provided yet
Recruitment and Hiring Report | Pending | Template has already been shared; Abhishek will revert with the timeline. |  |  | No Deadline has been provided yet
Promotion and Internal Movement Report | Pending | Template has already been shared; Abhishek will revert with the timeline. |  |  | No Deadline has been provided yet
Kinjal Ma'am Queries | Current Status | Remarks | Latest Remarks | Initial Deadline | New Deadline
Future date for applying OD is not available
AR and OD Excel report generation is not available even after multiple queries
Loan Section is not wokring
To access the details of Attendence, OD ,AR for all the employess that are working under such Managers who's reporting manager is Kinjal Ma'am
If an employee is on site and canno punch out , how can he apply for comp off next day?