## Sheet1
Pain Point by RML
S.No | HR's Queries | RML Resonse | Protiviti Response | RML Response | Bussiness User | Document Links | Protiviti's Response (1-7-2025) | RML Response (2/07/2025) | Protiviti's Response (2-7-2025) | Deadline to resolve the queries
1 | Travel Advance | Meeting to be fixed with Chandan Modi Ji for showcasing the solution | The leave credit has been done basis the data received from RML Team. Let us know we can check on case to case basis. | Denied | Sushanta Nayak |  | This is automated process. The credit of leave is suppose to be done on 1st of every month which is currently happening. We are exploring the option to make it happen by mid-night every month | Monthly leave credits have not been processed till now | They are getting credited today and the error occurred because of not approval of attendance as the leave balance depends on this.
2 | CEO Sirs Dashboard |  | The integration is working, we are awaiting information from IT Team for the same. | Under Progress | Sushanta Nayak |  | This is working we are waiting for RML IT Team to revert back | Today (02/07/2025), you have a meeting with the IT team. Kindly update us on the status post discussion. | Kent Team is checking as they have to change the way they are sending the information to greytHR
3 | Payslips is not updated as per Earlier (As per RML Format) |  | Payslips for Apr'25 and May'25 have been enabled. | Under Progress | Sushanta Nayak |  | Payslips are visible, please let us know your concern to address this issue | The same has been discussed with Protiviti, and a sample format has already been shared for reference | This is a new requirement which was not shared at the time of implementation. If any changes i..e adding of UAN or PAN the same can be incorporated
4 | PF No/UAN No has not been added for many people(Exp-Sushanta, Ashish Sir ) |  | As the data is provided the same has been updated in system | Has Been done as per the data shared | Sushanta Nayak |  | Please let us know your concern to address this issue | The concern has already been discussed with Protiviti, and a sample format was shared. The concern is related to information that needs to appear in the payslip. | Please let me know if the data has been provided and is still missing from greytHR
5 | Muster Report Download: It is mandatory that the reporting manager is present at the time of Muster Report(Attendance & leave) download to ensure accountability and data accuracy |  | It is already available and was showcased during all training provided to mangers. Approx.. 11 sessions have been conducted. | 2 Column needs to be added next to employee for Reporting Manager and Emp ID in muster report summary | Sapikul Ali | https://rashmimetaliks-my.sharepoint.com/:x:/r/personal/harish_kumar_rashmigroup_com/_layouts/15/Doc.aspx?sourcedoc=%7B3D373DB8-78A8-4C80-8186-65429E0BE698%7D&file=Attendance%20Muster%20Summary%20June%202025_%20-%20Copy.xlsx&action=default&mobileredirect=true | This is a new requirement which is now being asked. We are checking the feasibility and confirm. | This has been discussed earlier. Kindly let us know the expected timeline for its completion. | The report is created and the access is also provide to Mr.Vidya Sagar
6 | Daily Boarding & Exit Reporting: A daily email must be sent to the Plant Head reporting any new onboardings or removals of manpower. This is required without exception. |  | This is a new requirement which was not part of the implementation. Do share if this was mentioned in any email. If this is to be done it will be a customization and will be charged separately. | New Requirement | Sapikul Ali |  | This is a new requirement. We are checking the feasibility and confirm. | This has been discussed earlier. Kindly let us know the expected timeline for its completion. | This is a new requirement and feasibility to be checked. If can not be achieved then customisation cost will be shared.
7 | Employee Absenteeism (7–10 Days or More): Employees with continuous absence exceeding 7 to 10 days must be issued formal Warning / Show-Cause / Feedback emails through HR. This needs to be implemented strictly. |  | This is a new requirement which was not part of the implementation. Do share if this was mentioned in any email. If this is to be done it will be a customization and will be charged separately. | New Requirement | Sapikul Ali |  | This is a new requirement. We are checking the feasibility and confirm. | Requesting you to please confirm by when this can be completed. | This is a new requirement and feasibility to be checked. If can not be achieved then customisation cost will be shared.
8 | Cost Centre Updates: Cost centre-wise updates (such as for Substore) must be accurate. For example, when selecting Plant 1701, manpower cost should reflect correctly in the system. |  | what has been shared is already available in system please let us know if any data which was shared in this relation and is not available in greytHR. | 1 column must be there for showing the plant (or the Cost center) in which the employee is working | Sapikul Ali | https://rashmimetaliks-my.sharepoint.com/:x:/r/personal/harish_kumar_rashmigroup_com/_layouts/15/Doc.aspx?sourcedoc=%7B6382EE7D-5DAC-41A0-AFF6-528F2D45CCD8%7D&file=EmployeeSwipeDetails%20-%20Copy.xlsx&action=default&mobileredirect=true | This is a new requriement, however is already created in system the same can be showcase as and when needed. However to keep it updated the information must come from HR Team.
9 | Mismatch in Attendance Records: There are more than 200 employees whose attendance is showing 0, 1, or 1.5 days in greytHR, whereas they are physically present (confirmed through Kent system). In such cases, it is difficult to process removals without proper verification. The instruction given is that this process must be routed through an official HR email. |  | We had a call with the IT Team of RML and they confirmed that it is because of a concern with Kent system | 2 Column needs to be added next to employee for Reporting Manager and Emp ID in muster report summary | Sapikul Ali | https://rashmimetaliks-my.sharepoint.com/:x:/r/personal/harish_kumar_rashmigroup_com/_layouts/15/Doc.aspx?sourcedoc=%7B3D373DB8-78A8-4C80-8186-65429E0BE698%7D&file=Attendance%20Muster%20Summary%20June%202025_%20-%20Copy.xlsx&action=default&mobileredirect=true | As the Kent machines go offline the attendance is not captured or is captured late in Kent cloud. As a practice IT Team needs to run schedulers which are already provided by Kent on daily basis. Incase they do not perform this action it will keep on happening.
11 | Loan & Advance section not yet completed. |  | Till date we have not received any go ahead from RML HR Team if this module is to be enabled. | New Requirement | Sushanta Nayak |  | This is impelemented and already provided for testing | Kindly showcase the status | The same can be showcased after the payroll is finalised for the month i.e. on coming Monday
12 | Salary of new joiners are not avaiable in the system for the current month |  |  |  | Rachna |  | Kindly share the instance as when the employee is added the salary is also added specially for LOI cases. In case the employee is joininig directly if the salary is not provided by HR Team at that moment then it is added later | Shweta shares the details of every new joiner on their date of joining, which includes salary details, Cost Center, and Date of Joining (DOJ). | The same is not shared when LOIs are created if the same is provided then it can be included.
14 | The separation workflow has not been added, and as a result, the relieving and service certificates are yet to be issued. The resignation status records are not visible across different levels. |  |  |  | Rachna |  | The seperation flow is configured and we have already issued Relieving letters to employees | The letters were issued on the email request sent by Rachna. However that suppose to be done through the system once all levels of approval done at Greyt HR. Somewhere resignation flow was pending to be approved at admin level and nobady was assigned to that. | Let us know your availability to showcase and if changes are required the same can be set in system
15 | Reporting Manager name should be present in the Attendance & leave list whenever Download |  |  | New Requirement | Sushanta Nayak |  | This is a new requirement. We are checking the feasibility and confirm.
16 | AR & OD Excel Download option not Available |  |  |  | Sushanta Nayak |  | Need more clarity on this requirement | The options for Attendance Regularization and Off Duty report download are currently not available. | there is a report available in "Reports >> Query Builder >> Regularization And On Duty Report" please check that report for the required details
17 | Resigned & exited employees should not reflect to Active HR employee records |  |  |  | Rachna |  | What records are provided along with DOL the same are available in system. | Your team has to keep a track and check employee status . And mark inactive if employees have resigned | Currently we do not get the DOL for any case except those who are updating exit on the portal. This information is very critical for us to keep data updated.
18 | Employees are currently unable to apply for compensatory off through Greyt HR. |  |  |  | Rachna |  | Please share latest instance for checking | Emp Name: Rishab Sahoo is not able to apply for C-Off | Shared already applied comp-off by employees. As a admin you can check it from Workflow >> Monitor >> Leave Comp off
19 | Overtime Module |  |  |  | Sushanta Nayak |  | This is already implemented the OT will be sent to HODs for approval
20 | Offer Approval Procedure |  |  |  | Rachna |  | As ATS comes live this will form a part of that process. Also in case there will be exceptions the same can be handled seperatly as currenlty being handled.
21 | Attendance Tracking of Sales Employees |  |  |  | Sushanta Nayak |  | This is a new requirement. We are checking the feasibility and confirm. | As per the last meeting, you had confirmed that this is feasible. However, the list was also shared with you, and we are still awaiting action. | This is a new requriement which was never asked at the time of implementation. I confirmed that the same can be enabled however to enable anything we need to test and make sure there are no new concerns.
22 | Resource Deployment |  |  |  | Sushanta Nayak |  | All resources are deployed, let us know if there is any specific request | Kindly share the names along with their Date of Joining (DOJ) and also mention their respective designations. | Pleae refer to Sheet "Resource Details "
23 | ATS |  |  |  | Sushanta Nayak |  | In implementation and should be delived by July 5, 2025
24 | There should be an offer report that includes the candidate name, organizational unit, designation offered, date of joining, offer date, offered salary with probation percentage, and the LOI status (Accepted, Rejected, or Yet to Accept) |  |  | New Requirement | Rachna |  | Considering this is a new requriement we can share this report on weekly basis with Racha
25 | Attendance report that includes Dept, RM , contact no,Org unit |  |  | New Requirement | Rachna |  | Considering this is a new requriement we can share this report on weekly basis with Racha
26 | Onboarding and exit reports & (notifications) should be configured to notify the HR department, Business Head, and CEO Cell team |  |  | New Requirement | Rachna |  | This is a new requirement. We are checking the feasibility and confirm.

## Resource Details
S.No | Name | Designation | DOJ | DOL
1 | Pankaj Sinha | Senior Executive | 2025-05-19
2 | Dinesh J | Senior Executive | 2025-06-09
3 | Avigyan Das | Senior Executive | 2025-04-07 | 2025-07-17
4 | Aditya Anil | Senior Executive | 2025-05-26
5 | Pravin Gupta | Senior Executive | 2025-06-24
6 | Sourav Jana | Executive | 2025-05-19
7 | Sayar Gara | Executive | 2025-04-22
8 | Sujoy Dhara | Executive | 2025-06-14
9 | Mayank Kapoor | Executive | 2025-06-30