## PROTIVITI SOW
| 1.One Time setup | Status according to Protiviti | Status according to RML | Remarks from RML | Remarks from Protiviti | Bussiness User | NET_PROGRESS | Tasks Completed | Total Tasks
1 | perform changes on software as per client policies and requirements. | 50% | 50% | The required changes have not been fully implemented. |  | Shushanta Sir |  |  | 13420%
2 | Setup of client, employees and compensation master | 100% | 80% | Some employee compensation master is incomplete |  | Shushanta Sir |  |  | #REF! | 355
3 | Transfer of data for the previous months of the current financial year, the previous financial year any prior financial year before that as required in good faith. | 100% | 100% | complete data transfer done from adrenalin |  | Shushanta Sir
2.CORE HR-MODULE
SNO | Activities
1 | Employee Data Management:
2. CORE HR Module
2.1Employee Data Management
a | Management of centralized repository for employee master data, including personal, employment, and financial details. | 100% | 50% | The system is intended to manage employee data, including compensation, the compensation details are not being entered promptly when a new employee joins. As a result, we are unable to download compensation data for new joiners before current month payroll. |  | Rachna Ma'am
b | Providing secure access controls based on roles and permissions | 100% | 80% | leadership access granted as per the list, more users can be added |  | Rachna Ma'am
c | Integration with other Systems, as necessary. | 100% | 100% |  |  | Rachna Ma'am
| 2.2Compensation Structuring on Tool |  |  |  |  | Rachna Ma'am
a | Defining multiple pay structures based on grades, job levels, and locations. | 100% | 100% |  |  | Rachna Ma'am
b | handling basic pay, allowances, deductions, reimbursements, and performance-linked incentives. | 100% | 100% |  |  | Rachna Ma'am
c | customization for CTC breakup, flexi-benefits, and perquisites | 100% | 100% |  |  | Rachna Ma'am
3 | 2.3Policy Enforcement & Compliance Tracking |  |  |  |  | Rachna Ma'am
a | Platform automated policy updates on portal and employee communication | 100% | 100% | policy adherence is active , as per ready RML policies |  | Rachna Ma'am
b | Platform real-time tracking of policy adherence | 100% | 100% |  |  | Rachna Ma'am
c | Real-Time Policy Acknowledgement Tracking and automated alerts for non-compliance . | 100% | 100% | 100% |  | Rachna Ma'am
d | Platform Dashboard for HR and management reporting. | 100% | 0% | not ready |  | Rachna Ma'am
| 3. WORKFORCE Module |  |  |  |  | Rachna Ma'am
1 | 3.1Offer Management |  |  |  |  | Rachna Ma'am
a | Generation of offer letter and approvals. | 70% | 100% | The approval workflow has not been implemented yet. We had discussed enabling a one-level approval temporarily, to be activated upon ATS (Applicant Tracking System) implementation. However, this has not been done so far, and approvals are still being handled manually. |  | Rachna Ma'am
b | Tracking appointment letters. | 100% | 50% | after 1st may appointment letters can be issued , older they cannot issue bcos they have to run salary |  | Rachna Ma'am
2 | 3.2Onboarding & Employee Engagement |  |  | Incorrect employee codes (E-codes) have been generated, not adhering to the predefined series . Info reported by IT . Delay in creating ecodes. Our team is consistently required to send follow-up emails to the IT team for biometric registration and allocation of company assets to new joiners, as they do not take initiative to carry out these tasks independently and frequently seek support . Auto trigger to IT dept |  | Rachna Ma'am
a | Updation of candidate information by capturing through personal email. | 100% | 100% | It has been observed that a few candidates are not receiving the pre-joining link required to fill in their details. |  | Rachna Ma'am
b | Platform auto CTC structuring based on predefined templates. | 100% | 100% |  |  | Rachna Ma'am
c | Management of flexi-basket benefits and reimbursements. | 100% | 100% | RML to propose policy |  | Rachna Ma'am
d | Employee investment declarations for tax planning. | 100% | 100% |  |  | Rachna Ma'am
e | Employee loan processing on ESS portal and approval workflow . | 100% | 100% |  |  | Rachna Ma'am
f | Payslip and tax sheet generation for onboarding employees. | 100% | 100% |  |  | Rachna Ma'am
g | capturing previous employment details. | 100% | 100% |  |  | Rachna Ma'am
3 | 3.3Employee Confirmation Process |  |  |  |  | Rachna Ma'am
a | Probation review tracking and automated reminders | 90% | 100% | RML will know once probation is complete, Demo / Test to show by PV |  | Rachna Ma'am
b | Updating multi-level approval workflows for employee confirmation | 90% | 100% | RML will know once probation is complete |  | Rachna Ma'am
4 | 3.4Employee Transfers |  |  |  |  | Rachna Ma'am
a | Platform automated workflow for internal department/location transfers. | 100% | 100% |  |  | Rachna Ma'am
b | Platform-driven approvals and documentation updates. | 100% | 100% |  |  | Rachna Ma'am
c | compensation and role change updates in HRMS. | 100% | 100% |  |  | Rachna Ma'am
5 | 3.5Employee Separation & Exit Management |  |  |  |  | Rachna Ma'am
a | • Resignation initiation, tracking, and approval workflows. | 70% | 100% |  |  | Rachna Ma'am
b | • Digital clearance process across departments (IT, Admin, Finance) | 70% | 70% |  |  | Rachna Ma'am
c | • Final settlement and compliance with statutory requirements. | 100% | 100% |  |  | Rachna Ma'am
6 | 3.6Employee Letters Management |  |  |  |  | Rachna Ma'am
a | • Generation of various employee-related letters, including: o Experience letters o Relieving letters o Salary certificates | 100% | 100% | Not issued to employees who have already exited the organization |  | Rachna Ma'am
| 4. Leave& Attendance Management Module |  |  |  |  | Rachna Ma'am
1 | Shift Management |  |  |  |  | Rachna Ma'am
a | Defining and configuring multiple shift types (fixed, rotational, flexible, night shifts, etc.). | 100% | 50% | Roster has to be update by Mangers or has to be transfer to protivi by 5th of every month |  | Rachna Ma'am
b | Platform automated shift scheduling and roster management. | 100% | 100% | Reporting managers are unable to update shifts for their team members.Both reporting managers and employees are experiencing difficulties with attendance regularization |  | Rachna Ma'am
c | Integration with biometric systems. | 100% | 100% |  |  | Rachna Ma'am
2 | Attendance Tracking |  |  |  |  | Rachna Ma'am
a | management of real-time biometric attendance integration in system. | 70% | 90% | Employees who are working remotely are unable to apply for On-Duty (OD). This is causing challenges in accurately capturing and regularizing attendance for remote staff. |  | Rachna Ma'am
b | integration with access control systems for seamless tracking. | 70% | 90% |  |  | Rachna Ma'am
c | Platform automated late coming and early leaving reports. | 70% | 90% | policy adhered |  | Rachna Ma'am
d | Platform alerts for absenteeism, regularization requests, and policy violations | 70% | 90% |  |  | Rachna Ma'am
3 | Leave Management |  |  |  |  | Rachna Ma'am
a | Configuration of leave types (annual, sick, maternity, casual, etc.). | 100% | 100% | shift roaster to be updated by manager > weekly off can be considered for comp off |  | Rachna Ma'am
b | holiday calendar configuration by location and department. | 100% | 100% |  |  | Rachna Ma'am
c | • leave request and approval workflows with multi-level authorizations. | 100% | 100% |  |  | Rachna Ma'am
d | Platform automated leave balance tracking and accruals. | 100% | 100% |  |  | Rachna Ma'am
e | Leave encashment and carry-forward policies | 100% | 100% |  |  | Rachna Ma'am
4 | Overtime & Comp-Offs Management |  |  | Comm-off is working but OT module is not working |  | Rachna Ma'am
a | • overtime tracking based on pre-approved policies. | 100% | 100% |  |  | Rachna Ma'am
b | Platform auto-calculation of compensatory offs and extra working hours. | 100% | 100% |  |  | Rachna Ma'am
c | approval workflows for overtime requests. | 100% | 100% |  |  | Rachna Ma'am
d | integration with payroll for overtime | 100% | 100% |  |  | Rachna Ma'am
5 | Attendance Policy & Compliance |  |  |  |  | Rachna Ma'am
a | enforcement of attendance policies (minimum working hours, grace period, break time tracking). | 100% | 100% |  |  | Rachna Ma'am
b | Platform automated deductions and penalties for attendance violations. | 100% | 100% |  |  | Rachna Ma'am
c | Preparation of reports and dashboards for HR and management monitoring. | 100% |  | only leave dash board |  | Rachna Ma'am
5. Monthly payroll processing & Statutory Compliances
5.1 Payroll Processing
5. PROCESS RELATED TO MONTHLY SALARY PROCESSING (Timelines: As per agreed payroll calendarin the table below)
SNO | Activities
1 | Payroll Inputs Collection & Validation: Protiviti manages payroll inputs (new joiners, salary revisions, variable pay, deductions, loss of pay, etc.) in a predefined format. | 100% | 100% | Payroll inputs and all calculations given by Subhasis. They only run payroll for the month of May-25 |  | Shushanta Sir
2 | Investment & flexi declarations: Tax computation based on employee declarations via ESS portal | 100% | 100% | It is not completed via ESS portal. Data provided by RML |  | Shushanta Sir
3 | • Payroll processing & review: o Salary calculations with deductions and allowances. o Draft payroll reports for approval. o Final payroll processing after client confirmation | 100% | 100% |  |  | Shushanta Sir
4 | Performing Payroll deliverables: o Final Pay Register. o Bank Transfer File. o Journal Voucher Report. o Payslip & Tax computation slip via ESS. o Reimbursement & variance reports. | 100% | 100% | Final bank Transfer file and pay register prepared by Subhasis for May-25 payroll. |  | Shushanta Sir
5 | Preparation of standard & customized Reports: o Standard: TDS report, PF report, PT report, ESIC report, LWF report, Variance report, CTC report. o Customized: Cost Centre, Location, Department-wise reports. | 100% | 20% | Not Completed in ESS portal. CTC report available |  | Shushanta Sir
6 | • Calculation of OT(Over Time) charges and cross verifying with the attendance system and validate the OT charge | 100% | 100% | It is configured in may month, but it will be verified in june only. if worker worked on week off, any one to be approved either comp off or OT |  | Shushanta Sir
7 | • Protiviti should Handle the payroll Queries | 100% | 50% | Partially Handed by Protiviti |  | Shushanta Sir
8 | Protiviti should Validate attendance by verifying data or biometric records | 100% | 100% | Completed |  | Shushanta Sir
5.2 Verification of Inputs
9 | • The Protiviti should handle the end-to-end payroll process, from collecting inputs to preparing the final register | 100% | 50% | This is not being followed in practice ; the RML team is providing most of the inputs, and Protiviti is only executing the payroll run, showing a high level of dependency on the RML team. it has to be automated |  | Shushanta Sir
5.1 - Verification / Validation of Inputs:
SNO | Activities
1 | Effective date of salary revision. | 100% | 100% |  |  | Shushanta Sir
2 | Duplication of Employee Code / Number / ID. | 100% | 100% |  |  | Shushanta Sir
3 | Whether any employees are minor based on the date of birth. | 100% | 100% |  |  | Shushanta Sir
4 | Length of bank account. | 100% | 100% |  |  | Shushanta Sir
5 | IFSC code. | 100% | 100% |  |  | Shushanta Sir
6 | Permanent Account Number (PAN). | 100% | 100% |  |  | Shushanta Sir
7 | Aadhaar number. | 100% | 100% |  |  | Shushanta Sir
8 | Duplication of ESI number. | 100% | 100% |  |  | Shushanta Sir
9 | Check that the CTC matches with break up shared by the Rashmi Metaliks Limited | 100% | 100% |  |  | Shushanta Sir
10 | Identification of duplicate inputs. | 100% | 100% |  |  | Shushanta Sir
11 | Special Character for designation, Department - like" & " , ' ". These are not accepted and would be removed. | 100% | 100% |  |  | Shushanta Sir
12 | Check whether an employee is in Active or Inactive statusfor variable inputs. | 100% | 90% | Inactive employees are still appearing in the active employee list for variable inputs. |  | Shushanta Sir
5.3 Entity Transfer of Employes
5.2 - Payroll Calendar
SNO | Activities
1 | Payroll Input | 100% | 100% |  |  | Shushanta Sir
2 | Draft Pay sheet | 100% | 100% |  |  | Shushanta Sir
3 | Observations if any | 100% | 100% |  |  | Shushanta Sir
4 | Finaly pay Register | 100% | 100% | Done by RML Teams |  | Shushanta Sir
5 | Bank Transfer File | 100% | 100% | Done by RML Teams |  | Shushanta Sir
6 | Payslip and Tax planner | 100% | 100% |  |  | Shushanta Sir
7 | JV report, Standard report and Customised Reports | 100% | 100% |  |  | Shushanta Sir
5.3– Pro rating Salary / Calculation of Arrears
S No. | Activities
1 | 5.4 Pro rating Salary / Calculation of Arrears: |  |  |  |  | Shushanta Sir
a | Mid-month new joiner | 100% | 100% |  |  | Shushanta Sir
b | Mid-month leaver | 100% | 100% |  |  | Shushanta Sir
c | Loss of Pay calculations | 100% | 100% |  |  | Shushanta Sir
d | Loss of Pay reversals | 100% | 100% |  |  | Shushanta Sir
e | Previous month Loss of Pay | 100% | 100% |  |  | Shushanta Sir
2 | 5.4 Pro rating Salary / Calculation of Arrears: |  |  |  |  | Shushanta Sir
a | Actual calendar days in the month | 100% | 100% |  |  | Shushanta Sir
b | Actual calendar days in the month less weekends | 100% | 100% |  |  | Shushanta Sir
c | Fixed days like 30, 31 (this cannot change between months) without decimals. | 100% | 100% |  |  | Shushanta Sir
3 | Pro rating the salary based on the following factors is not possible: |  |  |  |  | Shushanta Sir
a | Actual calendar days less alternate weekends | 100% | 100% |  |  | Shushanta Sir
b | Actual calendar days less holidays | 100% | 100% |  |  | Shushanta Sir
c | Fixed days that vary month on month. | 100% | 100% |  |  | Shushanta Sir
3 | If the period for which salary is pro rated pertains to the period prior to go live with vendor, then the client would need provide arrear break up component wise to enable vendor to include in the current month payroll. | 100% | 100% |  |  | Shushanta Sir
Loan/Advance
S No. | Activities
1 | 5.5 Loans and Advances |  |  | The Loans and Advances module is currently not active |  | Shushanta Sir
2 | Vendor would handle the Loan scheduler with the following options: |  | 100% |  |  | Shushanta Sir
a. | Diminishing | 100% | 100% |  |  | Shushanta Sir
b. | Flat | 100% | 100% |  |  | Shushanta Sir
c. | Only EMI without Interest | 100% | 100% |  |  | Shushanta Sir
3 | vendor would calculate perquisites as per SBI lending rates. This is applicable only if the client provides the loan input to be recovered using vendor loan scheduler. If the client is giving the loan recovery amount month on month, then the client should provide the perquisite value. | 100% | 25% |  |  | Shushanta Sir
4 | In order to claim tax exemption for Home Loan & Interest employees would need to submit relevant proof to claim under Section 24 during end of year process. | 100% | 25% |  |  | Shushanta Sir
5 | Deductions against Salary advance should be provided as monthly inputs. | 100% | 25% |  |  | Shushanta Sir
6 | Vendor will not liaise with any third parties to deduct or remit loans and advances. | 100% | 25% |  |  | Shushanta Sir
5.5– Process for New Joiners
SNO | Activities
1 | 5.6 Process for New Joiners: |  |  |  |  | Shushanta Sir
a. | Throughout the month through Client portal | 100% | 100% |  |  | Shushanta Sir
b. | As part of monthly input through the excel format | 100% | 100% |  |  | Shushanta Sir
c. | Through HR connector if integration is in scope | 100% | 100% |  |  | Shushanta Sir
2 | New joiner details for the purpose of ESI IP generation need to be provided by the client once in a week. Flexi would be activated for new joiners after the first month payroll is processed. | 100% | 100% |  |  | Shushanta Sir
3 | ESS portal would be activated for new joiners |  | 100% |  |  | Shushanta Sir
a. | When client approves new joiner inputs via client portal | 100% | 100% |  |  | Shushanta Sir
b. | After first month payroll is processed if inputs are provided through excel format | 100% | 100% |  |  | Shushanta Sir
4 | At agreed interval if new joiner information is provided via HR connector | 100% | 100% |  |  | Shushanta Sir
| 5.7– Process for Salary hold and release |  |  | Currently it is Being Handel by RML |  | Panda Sir
1 | Scenario 1 (Payment hold) - To hold payment of any specific salary(s) vendor will process salary as instructed by the Rashmi Metaliks Limited. The salary transfer details in bank file will be removed. All statutory payments (PF, PT, ESI, LWF) would be remitted normally. In order to release the salary, Protiviti implant should add the net pay value of the employee as part of respective month's input | 100% | 100% | trial and tested |  | Panda Sir
2 | Scenario 2 (Process hold) - To hold processing of any specific salary(s) for absconding employees, etc., the Protiviti should include full month LOP input for this employee until the defined date. If the defined date is not known, Protiviti to give LOP input month on month. In order to release the salary, Protiviti should provide LOP reversal inputs in the respective month of release. | 100% | 100% | no input received yet from RML |  | Panda Sir
5.7– Additional General Scope
SNO | Activities
1 | 5.8 Additional General Scope: |  | 100% |  |  | Panda Sir
2 | Vendor would provide documentation support for any internal Audits and third-party requirements | 100% | 100% |  |  | Panda Sir
3 | Any data / reports requirement to support audit needs to be shared in advance with vendor and turnaround time to deliver will be mutually agreed. | 100% | 100% |  |  | Panda Sir
4 | Payroll processing for Interns / Trainees and apply statutory contributions (including tax) as applicable. | 100% | 100% |  |  | Panda Sir
5 | Payroll processing for Apprentice as per the Apprenticeship act without any statutory deduction. | 100% | 100% |  |  | Panda Sir
6 | Additional ad hoc/On Demand reports can be provided by vendor subject to feasibility. Timeline to build the report and commercials to be mutually agreed. | 100% | 100% |  |  | Panda Sir
| 5.9 Payroll Compliance & Statutory Reporting |  |  |  |  | Panda Sir
1 | Monthly Income TDS deductions and tax reporting | 100% | 0% |  |  | Panda Sir
2 | Quarterly filings (Form 24Q) & Annual Form 16 generation | 100% | 0% |  |  | Panda Sir
3 | Reconciliation of tax deductions vs. paid challans | 100% | 0% |  |  | Panda Sir
| 5.10 Provident Fund – In Scope |  |  |  |  | Panda Sir
1 | UAN generation & KYC updating. | 100% | 100% |  |  | Panda Sir
2 | PF challan & return filing | 100% | 100% |  |  | Panda Sir
3 | Inspection support & statutory queries resolution.is received in the mobile number registered in the EPFO Portal | 100% | 100% |  |  | Panda Sir
4 | EDLI Returns (Form 7IF) | 100% | 100% |  |  | Panda Sir
5 | Date of Leaving updating – Date of leaving and the reason for leaving will be updated in the EPFO portal by Protiviti | 100% | 100% | use case not received |  | Panda Sir
6 | Form 5A updating (Ownership Details) | 100% | 100% | use case not received |  | Panda Sir
7 | Modify Establishment Details | 100% | 100% | use case not received |  | Panda Sir
8 | Joint Declaration Submission | 100% | 100% | use case not received |  | Panda Sir
9 | Death Claim Submission | 100% | 100% | use case not received |  | Panda Sir
10 | Support in case of claim rejection by the EPFO | 100% | 100% | use case not received |  | Panda Sir
11 | Inspection Assistance / Response to the Notices | 100% | 100% | use case not received |  | Panda Sir
12 | Legislative Notification / Amendments | 100% | 100% | use case not received |  | Panda Sir
| 5.10 Employee State Insurance (ESIC) Compliance: |  |  |  |  | Panda Sir
1 | IP number generation, e-Pehchan card issuance. | 100% | 100% |  |  | Panda Sir
2 | ESIC contributions reporting & challan generation | 100% | 100% |  |  | Panda Sir
3 | ESIC half-yearly submission & compliance audits | 100% | 100% |  |  | Panda Sir
4 | Updating of family members details | 100% | 100% | no use case |  | Panda Sir
5 | Sharing ESIC Remitted Challan – Once the payment is made, Rashmi Metaliks Limited to download the paid challan from the ESIC Portal. | 100% | 100% |  |  | Panda Sir
6 | Documents Submission to ESIC Office for Employee Name, DOJ & Gender Correction (Protiviti Presence location) | 100% | 100% |  |  | Panda Sir
7 | Updating of Employer Details (Company Name, Address) | 100% | 100% |  |  | Panda Sir
| 5.10 Professional Tax (PT) Compliance: |  |  |  |  | Panda Sir
1 | PT computation, reporting & online remittance support | 100% | 0% |  |  | Panda Sir
2 | PT enrollment & renewal processing | 100% | 0% |  |  | Panda Sir
3 | PT - Enrolment Certificate - Remittance | 100% | 0% |  |  | Panda Sir
4 | PT - Enrolment Certificate - Returns | 100% | 0% |  |  | Panda Sir
5 | Company Tax Remittance | 100% | 0% |  |  | Panda Sir
6 | Sharing remitted /acknowledged challans | 100% | 0% |  |  | Panda Sir
7 | Inspection Assistance / Response to the Notices | 100% | 0% |  |  | Panda Sir
| 5.11 Labor Welfare Fund (LWF) Compliance |  |  |  |  | Panda Sir
1 | LWF data upload, challan generation & payment facilitation | 100% | 0% | june and december |  | Panda Sir
2 | LWF inspection assistance & compliance reporting | 100% | 0% |  |  | Panda Sir
| 5.13 Employee Self-Service (ESS) & Support |  |  |  |  | Panda Sir
1 | providing Employee Access: Payslips, tax computation slips, Form 16. Investment declarations & reimbursement claims. Tax calculator & helpdesk ticketing | 100% | 100% | format pending from HR |  | Panda Sir
2 | providing HR & Payroll SPOC Access: Bulk download of payroll & compliance reports. Employee onboarding & document management. Payroll discrepancy tracking & query resolution | 100% | 50% | Employees unable to update their family details |  | Panda Sir
| 5.14 Annual Processing & Compliance |  |  |  |  | Panda Sir
1 | Annual Bonus & Increment Processing: | 100% | 0% | no use case came |  | Panda Sir
2 | Tax Deduction & Year-End Adjustments | 100% | 0% |  |  | Panda Sir
S No. | 6.Reimbursement General Process
6.Salary related reimbursement processing
1 | Protiviti team should provide the following: > Reimbursement bank transfer > Reimbursement Register > Submission of reimbursement pay slip to employees via the Platform. > Calculation of TDS on the unclaimed entitlement at the year end or as per the Client policy > Assistance for management and resolution of desk queries raised by employees. | 0% | 80%
7.Engagement Module
7.1Employee Engagement Initiatives
1 | Broadcasting company news and updates in an engaging format. | 0% | 0%
2 | Enabling HR teams to share information and conduct opinion polls. | 0% | 0%
7.2 Employee Feedback & Pulse Surveys
1 | Conducting structured surveys for feedback collection. | 0% | 0%
2 | HR receives data-driven recommendations for improvements. | 0% | 0%
8. Asset Management
8.1 Asset Allocation & Tracking
1 | Platform for Asset Assignment | 0% | 70%
2 | Platform for management of Employee Asset Directory | 0% | 70%
8.2 Asset Maintenance & Compliance
1 | Platform for Asset Maintenance Scheduling | 0% | 70%
2 | Platform for Incident & Damage Reporting | 0% | 70%
8.3 Asset Retrieval & Exit Clearance
1 | Platform for Asset Return Process | 0% | 70%
2 | Platform for Clearance Workflows | 0% | 70%
3 | Platform for Lost or Unreturned Assets Management | 0% | 70%
9. Helpdesk
9.1 Ticketing System & Query Management
1 | Ticket Categories: Categorization of queries | 0% | 100%
2 | Platform Auto-Acknowledgment & Assignment: | 0% | 100%
9.2 Escalation & Resolution Workflow
1 | Escalation Matrix: Automated escalation of unresolved tickets based on pre-set SLAs | 0% | 0%
9.3 Helpdesk Reporting & Analytics
1 | Real-time tracking of open, pending, and resolved tickets. | 0% | 100%
2 | Monthly Performance Reports | 0% | 100%
| Total percentage completed | 87.85% | 81.33%
1 | Input Validations | 100% | 100%
| a. Value of individual pay components | 100% | 100%
| b. Matching of Employee Code / ID / Number with the Employee Name. vendor processes payroll based on Employee Code / ID / Number | 100% | 100%
2 | Processing off cycle payroll | 100% | 100%
|  | 16800% | 17000%
|  | 14808% | 13901%