## Sheet1
Task | RML | Protiviti | Remarks (RML) | Deadline
1.One Time setup
To perform changes on software as per client policies and requirements. | ✅ | ❌ | The required changes have not been fully implemented.
2. CORE HR Module
Platform Dashboard for HR and management reporting. |  |  | not ready | 2025-08-31
3. WORKFORCE Module
3.1Offer Management
Generation of offer letter and approvals.
3.3Employee Confirmation Process
Probation review tracking and automated reminders |  |  | Change of Approval flow & Team is working on it.
Updating multi-level approval workflows for employee confirmation |  |  | RML will know once probation is complete
3.5Employee Separation & Exit Management
Final settlement and compliance with statutory requirements. |  |  | FnF to run for 1st time in Aug 25 | 2025-08-18
4. Leave& Attendance Management Module
Overtime & Comp-Offs Management
overtime tracking based on pre-approved policies. |  |  | OT module implemented , automated application is not possible , manual done by Pro
Attendance Policy & Compliance
Preparation of reports and dashboards for HR and management monitoring. |  |  | only leave dash board NA
5. Monthly payroll processing & Statutory Compliances
5.5 Loans and Advances
Vendor would handle the Loan scheduler with the following options: |  |  | Loan / Advances before May 25 need to be integrated from SAP
5.14 Annual Processing & Compliance
Tax Deduction & Year-End Adjustments |  |  | tax deductions being done / yr end adjustment no use case came
7.Engagement Module
7.1Employee Engagement Initiatives
Enabling HR teams to share information and conduct opinion polls. |  |  | protiviti satisfaction poll to be initiated | 2025-08-12
7.2 Employee Feedback & Pulse Surveys
Conducting structured surveys for feedback collection. |  |  | protiviti satisfaction feedback to be initiated
8. Asset Management
8.2 Asset Maintenance & Compliance |  |  | actual demo to be done in ESS
Platform for Asset Maintenance Scheduling
Platform for Incident & Damage Reporting
Asset number filter is not available for assigning to employee
Field to be added to asset allocation to 3rd party
Warranty date cannot be updated to previous date
8.3 Asset Retrieval & Exit Clearance
Platform for Asset Return Process
Platform for Clearance Workflows
Platform for Lost or Unreturned Assets Management
10. Process Related to Final Settlement Processing |  |  |  | 2025-08-31
10.1 Process Related to Final settlement Process: |  |  | 1st FnF will be process in Aug 25
Settlement Input in Excel Format as shared by Protiviti viz – Number of days payable, Salary hold release, Leave Encashment days/Notice Pay recovery, Other Payments& Deductions, Gratuity, LTA claimed in previous employment
Protiviti should process payroll based on clarifications received (post verification of investment proofs and reimbursement claims submitted) and share the Final Settlement workings for confirmation
On receipt of confirmation, the following deliverables to be shared with the Rashmi Metaliks Limited SPOC
10.2 Full and Final Settlement Process-General |  |  | 1st FnF will be process in Aug 25
Protiviti should offers 2 Full and Final cycle.
The turnaround time to process Full and Final is 3 working days.
Protiviti would not interact with resigned employees and details would be shared only to SPOC.
“Alumni portal” access to exit employees need to be confirmedly Rashmi Metaliks Limited for RML to download