## PROTIVITI SOW
| MODULES | Status according to Protiviti | Status according to RML | Target Date | Remarks from RML | Remarks from Protiviti | NET_PROGRESS | Tasks Completed | Total Tasks | HRMS status (19 Oct 2026)
1.One Time setup
1 | perform changes on software as per client policies and requirements. |  | 50% |  | The required changes have not been fully implemented. |  |  |  |  | Partial — Most RML rules are now settings (cycle, LOP divisor, sandwich, statutory rates); OT pre-approval and penalty rules still missing.
2 | Setup of client, employees and compensation master |  | 100% | [6 empty] | Partial — Company, org masters, employee create/edit and salary assignment work; plants master and CTC-percentage templates missing.
3 | Transfer of data for the previous months of the current financial year, the previous financial year any prior financial year before that as required in good faith. |  | 100% |  | complete data transfer done from adrenalin |  |  |  |  | Partial — Excel importers and parallel-run register upload exist; Adrenalin/greytHR history not yet migrated into HRMS.
2. CORE HR Module
2.1Employee Data Management
a | Management of centralized repository for employee master data, including personal, employment, and financial details. |  | 100% | [6 empty] | Partial — Central employee master with create/edit and family details; ~79 joining-form fields and document uploads still missing.
b | Providing secure access controls based on roles and permissions |  | 100% | [6 empty] | Partial — Role and company/department scoping enforced; open gaps: HR can issue letters across companies, no MFA or auditor role.
c | Integration with other Systems, as necessary. |  | 100% | [6 empty] | Partial — Kent HTTP adapter and simulator built, awaiting real Kent access; SAP JV export exists; ATS/SSO not merged yet.
2.2Compensation Structuring on Tool
a | Defining multiple pay structures based on grades, job levels, and locations. |  | 100% | [6 empty] | Partial — Salary structures per company exist; no grade/location dimension and no percent-of-CTC rule, so one structure per employee.
b | handling basic pay, allowances, deductions, reimbursements, and performance-linked incentives. |  | 100% | [6 empty] | Partial — Earnings, deductions, reimbursement and incentive inputs handled in payroll; performance-linked incentive rules not automated.
c | customization for CTC breakup, flexi-benefits, and perquisites |  | 100% | [6 empty] | Partial — CTC breakup preview and validation exist; flexi-benefits not built; perquisites only as manual TDS input.
3 | 2.3Policy Enforcement & Compliance Tracking
a | Platform automated policy updates on portal and employee communication |  | 100% |  | policy adherence is active , as per ready RML policies |  |  |  |  | Partial — Policies publish on portal with weekly reminder job; email delivery not yet tested end to end.
b | Platform real-time tracking of policy adherence |  | 100% | [6 empty] | Partial — Policy acknowledgement status and report screens exist; reminders depend on untested email delivery.
c | Real-Time Policy Acknowledgement Tracking and automated alerts for non-compliance . |  | 100% | [6 empty] | Partial — Acknowledgement tracking and nag alerts exist; automatic alerts need email delivery testing.
d | Platform Dashboard for HR and management reporting. |  | 0% | 2025-08-31 | not ready |  |  |  |  | Partial — HR, plant and leadership dashboards built; HR head blocked from executive page, HOD dashboard shows zeros.
3. WORKFORCE Module
1 | 3.1Offer Management
a | Generation of offer letter and approvals. |  | 70% |  | Once the ATS get implemented it will get solved |  |  |  |  | Missing — No offer letter or LOI generation and approval in HRMS; only an offers report from ATS data.
b | Tracking appointment letters. |  | 100% |  | Letter is geting generated and is available on ESS portal |  |  |  |  | Partial — Appointment letter template, issue and ESS 'My letters' exist; issuance tracking not verified end to end.
2 | 3.2Onboarding & Employee Engagement
a | Updation of candidate information by capturing through personal email. |  | 100% |  | It has been observed that a few candidates are not receiving the pre-joining link required to fill in their details. |  |  |  |  | Partial — Pre-join link portal captures candidate details; email delivery untested and conversion skips ID validations.
b | Platform auto CTC structuring based on predefined templates. |  | 100% | [6 empty] | Missing — Templates cannot derive Basic/HRA from CTC (bug open), so auto CTC structuring is not possible yet.
c | Management of flexi-basket benefits and reimbursements. |  | 100% |  | RML to propose policy |  |  |  |  | Partial — Claims/reimbursement module exists but blocks claims without a budget; flexi-basket not built.
d | Employee investment declarations for tax planning. |  | 100% | [6 empty] | Partial — ESS tax page: regime choice, 80C/80D/NPS declarations with proof upload; no HRA/Section 24 or proof verification screen.
e | Employee loan processing on ESS portal and approval workflow . |  | 100% | [6 empty] | Partial — Loan apply with eligibility and RM→HR→payroll approval exists; employees currently can't open the loan page (bug).
f | Payslip and tax sheet generation for onboarding employees. |  | 100% | [6 empty] | Partial — ESS payslips and Form 16 available; tax computation sheet for joiners not verified.
g | capturing previous employment details. |  | 100% | [6 empty] | Partial — Only previous employer name captured on candidate; no employment history grid or Form 12B income capture.
3 | 3.3Employee Confirmation Process
a | Probation review tracking and automated reminders |  | 70% | 2025-08-13 | Change of Approval flow & Team is working on it. |  |  |  |  | Partial — Probation board with due alerts and reviews works; reminder emails untested.
b | Updating multi-level approval workflows for employee confirmation |  | 70% |  | RML will know once probation is complete |  |  |  |  | Partial — Confirmation chain RM → HR head configured; not exercised end to end yet.
4 | 3.4Employee Transfers
a | Platform automated workflow for internal department/location transfers. |  | 100% | [6 empty] | Partial — Transfer request with RM → HR ops approval and future-dated apply exists; end-to-end check not done.
b | Platform-driven approvals and documentation updates. |  | 100% | [6 empty] | Partial — Transfer approvals and history exist; documentation/letter update on transfer not verified.
c | compensation and role change updates in HRMS. |  | 100% | [6 empty] | Partial — Transfer can change grade/designation; pay change is a separate salary revision, not linked.
5 | 3.5Employee Separation & Exit Management
a | • Resignation initiation, tracking, and approval workflows. |  | 100% | [6 empty] | Partial — Employee resignation submits correctly, but employees can't reach the form or see status; no separation types.
b | • Digital clearance process across departments (IT, Admin, Finance) |  | 100% | [6 empty] | Partial — Department clearance list and sign-off exist; not verified end to end.
c | • Final settlement and compliance with statutory requirements. |  | 70% | 2025-08-18 | FnF to run for 1st time in Aug 25 |  |  |  |  | Partial — F&F and gratuity calculation tested; F&F can be paid twice (fix not on main yet).
6 | 3.6Employee Letters Management
a | • Generation of various employee-related letters, including: o Experience letters o Relieving letters o Salary certificates |  | 100% | [6 empty] | Partial — Experience, relieving and salary-certificate templates with issue; letter issue ignores company scope (security bug).
4. Leave& Attendance Management Module
1 | Shift Management
a | Defining and configuring multiple shift types (fixed, rotational, flexible, night shifts, etc.). |  | 100% | [6 empty] | Partial — Fixed, two-session, general and night shifts configurable; rotational patterns and half-day session timings missing.
b | Platform automated shift scheduling and roster management. |  | 100% | [6 empty] | Partial — Monthly roster view and edit with reminder job; no automatic rotational scheduling.
c | Integration with biometric systems. |  | 100% | [6 empty] | Partial — Kent adapter, simulator and punch import built; real Kent connection details still awaited.
2 | Attendance Tracking
a | management of real-time biometric attendance integration in system. |  | 100% | [6 empty] | Partial — Punch-to-day-status pipeline proven with simulator; live Kent feed and webhook not on main.
b | integration with access control systems for seamless tracking. |  | 100% | [6 empty] | Partial — Device and door health screen exists; no direct access-control system integration beyond Kent.
c | Platform automated late coming and early leaving reports. |  | 100% |  | policy adhered |  |  |  |  | Partial — Late/early minutes computed and exceptions report exists; RML grace/penalty slabs not configured.
d | Platform alerts for absenteeism, regularization requests, and policy violations |  | 100% | [6 empty] | Partial — Absence cases, regularisation approvals and scans exist; alert emails untested, background worker crashes on fresh install.
3 | Leave Management
a | Configuration of leave types (annual, sick, maternity, casual, etc.). |  | 100% | [6 empty] | Done — Seven leave types (CL, SL, EL, ML, CO, LWP, Election) configured with rules and gender applicability.
b | holiday calendar configuration by location and department. |  | 100% | [6 empty] | Partial — Holidays by group, company, plant or location via API/Excel; screen only picks location; no department calendars.
c | • leave request and approval workflows with multi-level authorizations. |  | 100% | [6 empty] | Partial — Apply, approve, reject, send-back work with configurable chains; no cancel button for employees.
d | Platform automated leave balance tracking and accruals. |  | 100% | [6 empty] | Partial — Balances, ledger and daily accrual job exist; background worker fails on fresh install (bug open).
e | Leave encashment and carry-forward policies |  | 100% | [6 empty] | Partial — Encashment and year-end carry-forward exist in backend; no employee encashment screen.
4 | Overtime & Comp-Offs Management |  |  |  | Comm-off is working but OT module is not working
a | • overtime tracking based on pre-approved policies. |  | 50% |  | OT module implemented , automated application is not possible , manual done by Pro |  |  |  |  | Partial — OT detected from punches with caps and manager approval; OT pre-approval not built.
b | Platform auto-calculation of compensatory offs and extra working hours. |  | 100% | [6 empty] | Partial — Comp-off conversion and expiry exist; auto-calculation not verified end to end.
c | approval workflows for overtime requests. |  | 100% | [6 empty] | Done — OT approval workflow and manager OT decisions screen work; employees can't self-approve.
d | integration with payroll for overtime |  | 100% | [6 empty] | Partial — Approved OT flows into payroll and tested; OT rate rule (base) awaiting client decision.
5 | Attendance Policy & Compliance
a | enforcement of attendance policies (minimum working hours, grace period, break time tracking). |  | 100% | [6 empty] | Partial — Grace, minimum hours, half-day and missed-punch rules applied; break-time tracking not built.
b | Platform automated deductions and penalties for attendance violations. |  | 100% | [6 empty] | Partial — Week-off and sandwich rules affect pay; late-coming penalty slabs empty, no penalty deductions configured.
c | Preparation of reports and dashboards for HR and management monitoring. |  |  |  | only leave dash board NA |  |  |  |  | Partial — Muster, swipe, regularisation, exceptions, OT and absence reports exist; muster needs manual company ID and rebuild.
5. Monthly payroll processing & Statutory Compliances
5.1 Payroll Processing
1 | Payroll Inputs Collection & Validation: Protiviti manages payroll inputs (new joiners, salary revisions, variable pay, deductions, loss of pay, etc.) in a predefined format. |  | 100% | [6 empty] | Partial — Payroll inputs via Excel/Report 4 upload with validation; no maker-checker or pre-payroll missing-ID check.
2 | Investment & flexi declarations: Tax computation based on employee declarations via ESS portal |  | 100% | [6 empty] | Partial — TDS uses ESS declarations and regime; HRA, Section 24 and flexi declarations not supported.
3 | • Payroll processing & review: o Salary calculations with deductions and allowances. o Draft payroll reports for approval. o Final payroll processing after client confirmation |  | 100% | [6 empty] | Partial — Draft → review → co-sign → finalise works, recon 44/44 matches; reopened runs can't edit inputs.
4 | Performing Payroll deliverables: o Final Pay Register. o Bank Transfer File. o Journal Voucher Report. o Payslip & Tax computation slip via ESS. o Reimbursement & variance reports. |  | 100% |  | Working day logic corrected as per RML which will reflected from Aug payroll |  |  |  |  | Partial — Pay register, bank file, SAP JV, payslips, variance exist; duplicate bank batches possible, JV needs missing plants master.
5 | Preparation of standard & customized Reports: o Standard: TDS report, PF report, PT report, ESIC report, LWF report, Variance report, CTC report. o Customized: Cost Centre, Location, Department-wise reports. |  | 100% | [6 empty] | Partial — PF ECR, ESIC, PTRC, LWF Form D, 24Q, variance exist; cost-centre/location/department custom reports limited.
6 | • Calculation of OT(Over Time) charges and cross verifying with the attendance system and validate the OT charge |  | 100% | [6 empty] | Partial — OT pay computed from approved attendance OT; rate basis awaiting client decision.
7 | • Protiviti should Handle the payroll Queries |  | 100% | [6 empty] | Not software — Vendor service; HRMS supports it through Helpdesk tickets with a payroll query category.
8 | Protiviti should Validate attendance by verifying data or biometric records |  | 100% | [6 empty] | Partial — Month-lock checklist validates attendance before payroll; unmatched swipes at one plant block every company (bug).
5.2 Verification of Inputs
9 | • The Protiviti should handle the end-to-end payroll process, from collecting inputs to preparing the final register |  | 100% | [6 empty] | Partial — Full input-to-register pipeline works on test data; fresh-install worker crash blocks month lock (bug open).
1 | Effective date of salary revision. |  | 100% | [6 empty] | Done — Salary revisions take an effective date; back-dated revisions generate arrears automatically.
2 | Duplication of Employee Code / Number / ID. |  | 100% | [6 empty] | Done — Employee codes auto-allocated and unique in the database; importer rejects duplicates.
3 | Whether any employees are minor based on the date of birth. |  | 100% | [6 empty] | Partial — Under-18 check on HR create/edit and Excel import; pre-join conversion skips it (bug open).
4 | Length of bank account. |  | 100% | [6 empty] | Partial — Bank account 9–18 digit check on create/edit and import; pre-join conversion skips it.
5 | IFSC code. |  | 100% | [6 empty] | Partial — IFSC format check on create/edit and import; pre-join only checks length 11.
6 | Permanent Account Number (PAN). |  | 100% | [6 empty] | Partial — PAN format check on create/edit and import; pre-join conversion skips full validation.
7 | Aadhaar number. |  | 100% | [6 empty] | Partial — Aadhaar 12-digit checksum validation on create/edit and import; pre-join conversion skips it.
8 | Duplication of ESI number. |  | 100% | [6 empty] | Partial — Duplicate ESIC/UAN/PAN/Aadhaar blocked on create/edit and import; pre-join conversion not checked.
9 | Check that the CTC matches with break up shared by the Rashmi Metaliks Limited |  | 100% | [6 empty] | Partial — CTC vs breakup validation exists; structures can't be driven from CTC yet (bug open).
10 | Identification of duplicate inputs. |  | 100% | [6 empty] | Partial — Duplicate rows within an upload and repeat files are caught; no employee code/name match check.
11 | Special Character for designation, Department - like" & " , ' ". These are not accepted and would be removed. |  | 100% | [6 empty] | Missing — No cleaning or blocking of special characters in designation or department names.
12 | Check whether an employee is in Active or Inactive statusfor variable inputs. |  | 100% | [6 empty] | Partial — Run includes only eligible active staff; variable inputs for exited/inactive employees aren't blocked.
5.3 Entity Transfer of Employes
1 | Payroll Input |  | 100% | [6 empty] | Partial — Entity transfer exists; payroll split between two companies in one month not proven.
2 | Draft Pay sheet |  | 100% | [6 empty] | Partial — Draft pay sheet available per company run; transfer-month split not verified.
3 | Observations if any |  | 100% | [6 empty] | Partial — Variance report available; transfer-specific observations not verified.
4 | Finaly pay Register |  | 100% | [6 empty] | Partial — Final pay register per company exists; transfer-month handling not verified.
5 | Bank Transfer File |  | 100% | [6 empty] | Partial — Bank file per company exists; duplicate batches possible and transfer month not verified.
6 | Payslip and Tax planner |  | 100% | [6 empty] | Partial — Payslip and Form 16 exist; separate tax planner per entity not verified.
7 | JV report, Standard report and Customised Reports |  | 100% | [6 empty] | Partial — SAP JV and standard reports exist; JV setup needs plants master (missing).
1 | 5.4 Pro rating Salary / Calculation of Arrears:
a | Mid-month new joiner |  | 100% | [6 empty] | Done — Mid-month joiner proration tested in scenario matrix and payroll reconciliation.
b | Mid-month leaver |  | 100% | [6 empty] | Done — Mid-month leaver proration tested; leaver pay stops at approved last working day.
c | Loss of Pay calculations |  | 100% | [6 empty] | Done — LOP from attendance tested across divisors, half days and sandwich rule; muster LOP equals payslip.
d | Loss of Pay reversals |  | 100% | [6 empty] | Partial — Engine supports LOP reversal days; no clear screen to enter reversals on the run.
e | Previous month Loss of Pay |  | 100% | [6 empty] | Partial — Late LOP after cut-off is deducted next month; manual prior-month LOP adjustments not verified.
2 | 5.4 Pro rating Salary / Calculation of Arrears:
a | Actual calendar days in the month |  | 100% | [6 empty] | Done — Calendar-days divisor is the default and tested.
b | Actual calendar days in the month less weekends |  | 100% | [6 empty] | Done — Working-days and fixed-26 divisors exclude week-offs; tested in scenario matrix.
c | Fixed days like 30, 31 (this cannot change between months) without decimals. |  | 100% | [6 empty] | Partial — Fixed 30 and 26-day divisors exist; no fixed 31-day option.
3 | Pro rating the salary based on the following factors is not possible:
a | Actual calendar days less alternate weekends |  | 100% | [6 empty] | Not software — SOW marks this proration method as not possible; no software needed.
b | Actual calendar days less holidays |  | 100% | [6 empty] | Not software — SOW marks this as not possible (HRMS working-days divisor already excludes holidays).
c | Fixed days that vary month on month. |  | 100% | [6 empty] | Not software — SOW marks this proration method as not possible; no software needed.
3 | If the period for which salary is pro rated pertains to the period prior to go live with vendor, then the client would need provide arrear break up component wise to enable vendor to include in the current month payroll. |  | 100% | [6 empty] | Partial — Back-dated revisions create arrears; component-wise arrear input for pre-go-live periods not verified.
1 | 5.5 Loans and Advances
2 | Vendor would handle the Loan scheduler with the following options: |  | 70% |  | Loan / Advances before May 25 need to be integrated from SAP |  |  |  |  | Partial — Loan scheduler with approval exists; employees can't open apply page; pre-May-25 SAP loans need import.
a. | Diminishing |  | 100% | 2025-08-31 | Loan eligibility is being calc to Basic |  |  |  |  | Partial — Diminishing-balance schedule calculated; blocked for employees by loan page access bug.
b. | Flat |  | 100% | [6 empty] | Partial — Flat-interest schedule calculated; blocked for employees by loan page access bug.
c. | Only EMI without Interest |  | 100% | [6 empty] | Partial — Interest-free EMI schedule calculated; blocked for employees by loan page access bug.
3 | vendor would calculate perquisites as per SBI lending rates. This is applicable only if the client provides the loan input to be recovered using vendor loan scheduler. If the client is giving the loan recovery amount month on month, then the client should provide the perquisite value. |  | 100% | [6 empty] | Partial — Loan perquisite calculation code exists; SBI rate source and payroll flow not verified.
4 | In order to claim tax exemption for Home Loan & Interest employees would need to submit relevant proof to claim under Section 24 during end of year process. |  | 100% | [6 empty] | Missing — Proof upload exists for 80C etc., but no Section 24 home-loan interest declaration.
5 | Deductions against Salary advance should be provided as monthly inputs. |  | 100% | [6 empty] | Done — Salary advance recoveries can be entered as monthly payroll deduction inputs.
6 | Vendor will not liaise with any third parties to deduct or remit loans and advances. |  | 100% | [6 empty] | Not software — Vendor obligation, no software needed.
1 | 5.6 Process for New Joiners:
a. | Throughout the month through Client portal |  | 100% | [6 empty] | Partial — HR can add joiners anytime via pre-join portal or employee form; conversion skips validations.
b. | As part of monthly input through the excel format |  | 100% | [6 empty] | Partial — New joiners can be uploaded via Excel template in Data imports; many joining-form fields missing.
c. | Through HR connector if integration is in scope |  | 100% | [6 empty] | Partial — Candidate ingest API exists; ATS/HR connector is on an unmerged branch, not on main.
2 | New joiner details for the purpose of ESI IP generation need to be provided by the client once in a week. Flexi would be activated for new joiners after the first month payroll is processed. |  | 100% | [6 empty] | Not software — Client process commitment; HRMS only supplies the data.
3 | ESS portal would be activated for new joiners
a. | When client approves new joiner inputs via client portal |  | 100% | [6 empty] | Partial — Login created when HR converts a candidate; activation flow not verified end to end.
b. | After first month payroll is processed if inputs are provided through excel format |  | 100% | [6 empty] | Partial — ESS shows payslips once the first payroll is finalised; Excel-route activation not verified.
4 | At agreed interval if new joiner information is provided via HR connector |  | 100% | [6 empty] | Partial — Depends on HR connector, which is not on main yet.
5.7– Process for Salary hold and release
1 | Scenario 1 (Payment hold) - To hold payment of any specific salary(s) vendor will process salary as instructed by the Rashmi Metaliks Limited. The salary transfer details in bank file will be removed. All statutory payments (PF, PT, ESI, LWF) would be remitted normally. In order to release the salary, Protiviti implant should add the net pay value of the employee as part of respective month's input |  | 100% | [6 empty] | Partial — Payment hold/release API exists; holds not visible on the payroll run screen.
2 | Scenario 2 (Process hold) - To hold processing of any specific salary(s) for absconding employees, etc., the Protiviti should include full month LOP input for this employee until the defined date. If the defined date is not known, Protiviti to give LOP input month on month. In order to release the salary, Protiviti should provide LOP reversal inputs in the respective month of release. |  | 100% | [6 empty] | Partial — Process hold via LOP and absconding flow exists; release/reversal not shown on run screen.
1 | 5.8 Additional General Scope:
2 | Vendor would provide documentation support for any internal Audits and third-party requirements |  | 100% | [6 empty] | Partial — Tamper-evident audit log with verify and Excel exports; some modules don't write audit entries.
3 | Any data / reports requirement to support audit needs to be shared in advance with vendor and turnaround time to deliver will be mutually agreed. |  | 100% | [6 empty] | Not software — Service/turnaround commitment, no software needed.
4 | Payroll processing for Interns / Trainees and apply statutory contributions (including tax) as applicable. |  | 100% | [6 empty] | Partial — Trainee category exists with normal statutory rules; payroll for trainees not verified.
5 | Payroll processing for Apprentice as per the Apprenticeship act without any statutory deduction. |  | 100% | [6 empty] | Partial — Apprentice no-deduction rule exists in code; not verified in a payroll run.
6 | Additional ad hoc/On Demand reports can be provided by vendor subject to feasibility. Timeline to build the report and commercials to be mutually agreed. |  | 100% | [6 empty] | Not software — Commercial service term; HRMS reports already export to Excel.
5.9 Payroll Compliance & Statutory Reporting
1 | Monthly Income TDS deductions and tax reporting |  | 100% |  | Handling only white collars |  |  |  |  | Partial — Monthly TDS (new/old regime, surcharge, 87A) tested; limited declarations and outdated slab table.
2 | Quarterly filings (Form 24Q) & Annual Form 16 generation |  | 100% | [6 empty] | Done — Form 24Q quarterly data (CSV) and Form 16 PDF generated, with payroll and ESS screens.
3 | Reconciliation of tax deductions vs. paid challans |  | 100% | [6 empty] | Done — TDS challans recorded and reconciled month by month against TDS deducted.
5.10 Provident Fund – In Scope
1 | UAN generation & KYC updating. |  | 100% | [6 empty] | Not software — EPFO portal service task, not software.
2 | PF challan & return filing |  | 100% | [6 empty] | Partial — PF ECR file generated; pension (EPS) split wrong for new high-wage members and over-58s.
3 | Inspection support & statutory queries resolution.is received in the mobile number registered in the EPFO Portal |  | 100% | [6 empty] | Not software — EPFO service task, not software.
4 | EDLI Returns (Form 7IF) |  | 100% | [6 empty] | Not software — EPFO service task, not software.
5 | Date of Leaving updating – Date of leaving and the reason for leaving will be updated in the EPFO portal by Protiviti |  | 100% | [6 empty] | Not software — EPFO portal service task, not software.
6 | Form 5A updating (Ownership Details) |  | 100% | [6 empty] | Not software — EPFO service task, not software.
7 | Modify Establishment Details |  | 100% | [6 empty] | Not software — EPFO service task, not software.
8 | Joint Declaration Submission |  | 100% | [6 empty] | Not software — EPFO service task, not software.
9 | Death Claim Submission |  | 100% | [6 empty] | Not software — EPFO service task, not software.
10 | Support in case of claim rejection by the EPFO |  | 100% | [6 empty] | Not software — EPFO service task, not software.
11 | Inspection Assistance / Response to the Notices |  | 100% | [6 empty] | Not software — Statutory service task, not software.
12 | Legislative Notification / Amendments |  | 100% | [6 empty] | Not software — Legal tracking service; statutory rates are editable versioned settings in HRMS.
5.10 Employee State Insurance (ESIC) Compliance:
1 | IP number generation, e-Pehchan card issuance. |  | 100% | [6 empty] | Not software — ESIC portal service task, not software.
2 | ESIC contributions reporting & challan generation |  | 100% | [6 empty] | Partial — ESIC return file and ₹21,000 eligibility rule tested; challan generation is on the ESIC portal.
3 | ESIC half-yearly submission & compliance audits |  | 100% | [6 empty] | Not software — ESIC service task, not software.
4 | Updating of family members details |  | 100% | [6 empty] | Not software — ESIC portal task; HRMS family details change flow (ESS → HR approval) exists.
5 | Sharing ESIC Remitted Challan – Once the payment is made, Rashmi Metaliks Limited to download the paid challan from the ESIC Portal. |  | 100% | [6 empty] | Not software — Client/portal task, not software.
6 | Documents Submission to ESIC Office for Employee Name, DOJ & Gender Correction (Protiviti Presence location) |  | 100% | [6 empty] | Not software — ESIC office service task, not software.
7 | Updating of Employer Details (Company Name, Address) |  | 100% | [6 empty] | Not software — ESIC portal task; company statutory details editable in HRMS org masters.
5.10 Professional Tax (PT) Compliance:
1 | PT computation, reporting & online remittance support |  | 100% | [6 empty] | Partial — West Bengal PT computed and tested, PTRC report exists; remittance is on the state portal.
2 | PT enrollment & renewal processing |  | 100% | [6 empty] | Not software — PT enrolment service task, not software.
3 | PT - Enrolment Certificate - Remittance |  | 100% | [6 empty] | Not software — PT service task, not software.
4 | PT - Enrolment Certificate - Returns |  | 100% | [6 empty] | Not software — PT service task, not software.
5 | Company Tax Remittance |  | 100% | [6 empty] | Not software — PT service task, not software.
6 | Sharing remitted /acknowledged challans |  | 100% | [6 empty] | Not software — Service task, not software.
7 | Inspection Assistance / Response to the Notices |  | 100% | [6 empty] | Not software — Statutory service task, not software.
5.11 Labor Welfare Fund (LWF) Compliance
1 | LWF data upload, challan generation & payment facilitation |  | 100% | [6 empty] | Partial — LWF deducted and Form D statement exists; no challan or upload file.
2 | LWF inspection assistance & compliance reporting |  | 100% | [6 empty] | Not software — Statutory service task, not software.
5.13 Employee Self-Service (ESS) & Support
1 | providing Employee Access: Payslips, tax computation slips, Form 16. Investment declarations & reimbursement claims. Tax calculator & helpdesk ticketing |  | 100% | [6 empty] | Partial — ESS payslips, Form 16, declarations, claims and helpdesk exist; claims blocked without budget, limited tax sections.
2 | providing HR & Payroll SPOC Access: Bulk download of payroll & compliance reports. Employee onboarding & document management. Payroll discrepancy tracking & query resolution |  | 100% |  | We can make mandatory data for old employee fill by employee before using ESS portal |  |  |  |  | Partial — Bulk reports, onboarding and helpdesk exist; no document upload/verification management.
5.14 Annual Processing & Compliance
1 | Annual Bonus & Increment Processing: |  | 100% | [6 empty] | Partial — Increment simulation/batch and bonus true-up exist; not verified end to end.
2 | Tax Deduction & Year-End Adjustments |  | 50% |  | tax deductions being done / yr end adjustment no use case came |  |  |  |  | Partial — TDS computed monthly; year-end adjustment and claims recovery exist but untested.
6.Salary related reimbursement processing
1 | Protiviti team should provide the following: > Reimbursement bank transfer > Reimbursement Register > Submission of reimbursement pay slip to employees via the Platform. > Calculation of TDS on the unclaimed entitlement at the year end or as per the Client policy > Assistance for management and resolution of desk queries raised by employees. |  | 100% | [6 empty] | Partial — Claims payout, register and claims report exist; claims blocked without budget, reimbursement payslip not verified.
7.Engagement Module
7.1Employee Engagement Initiatives
1 | Broadcasting company news and updates in an engaging format. |  | 100% |  | module ready |  |  |  |  | Partial — Announcements module with publish and feed works; audience targeting not fully verified.
2 | Enabling HR teams to share information and conduct opinion polls. |  | 0% | 2025-08-12 | protiviti satisfaction poll to be initiated |  |  |  |  | Partial — Polls with create, respond and results exist; not used live yet.
7.2 Employee Feedback & Pulse Surveys
1 | Conducting structured surveys for feedback collection. |  | 0% |  | protiviti satisfaction feedback to be initiated |  |  |  |  | Partial — Surveys with create, respond and results exist; answer validation gaps remain.
2 | HR receives data-driven recommendations for improvements. |  | 100% | [6 empty] | Missing — No data-driven recommendations; only raw survey and poll results.
8. Asset Management
8.1 Asset Allocation & Tracking
1 | Platform for Asset Assignment |  | 100% | [6 empty] | Done — Assets can be assigned to employees or third parties from the Assets screen.
2 | Platform for management of Employee Asset Directory |  | 100% | [6 empty] | Done — Searchable asset register with holder, warranty and Excel export.
8.2 Asset Maintenance & Compliance
1 | Platform for Asset Maintenance Scheduling |  | 50% |  | actual demo to be done in ESS |  |  |  |  | Partial — Maintenance log per asset exists; no scheduling or due reminders.
2 | Platform for Incident & Damage Reporting |  | 50% | [6 empty] | Partial — Incidents logged as maintenance entries; no separate damage reporting workflow.
8.3 Asset Retrieval & Exit Clearance
1 | Platform for Asset Return Process |  | 50% | [6 empty] | Partial — Asset return action exists; not automatically linked to exit clearance.
2 | Platform for Clearance Workflows |  | 50% | [6 empty] | Partial — Exit clearance across IT, Admin, Finance exists; asset linkage and end-to-end test pending.
3 | Platform for Lost or Unreturned Assets Management |  | 50% | [6 empty] | Partial — Non-returned assets list and export exist; no lost-asset recovery workflow.
9. Helpdesk
9.1 Ticketing System & Query Management
1 | Ticket Categories: Categorization of queries |  | 100% | [6 empty] | Done — Helpdesk categories with owner role and SLA, visible to all users.
2 | Platform Auto-Acknowledgment & Assignment: |  | 100% | [6 empty] | Partial — Tickets auto-assigned by category role; acknowledgement email not yet tested.
9.2 Escalation & Resolution Workflow
1 | Escalation Matrix: Automated escalation of unresolved tickets based on pre-set SLAs |  | 100% |  | this has to be tested |  |  |  |  | Partial — Hourly SLA escalation job exists; untested, and worker crashes on fresh install.
9.3 Helpdesk Reporting & Analytics
1 | Real-time tracking of open, pending, and resolved tickets. |  | 100% | [6 empty] | Partial — Ticket lists by status for agents; reopen history gap remains.
2 | Monthly Performance Reports |  | 100% | [6 empty] | Partial — Helpdesk performance report and export exist; not verified with real data.
9.4 Compliance & Audit Support
1 | Helpdesk Query Logs |  | 100% | [6 empty] | Partial — Ticket threads and status history stored; reopen history incomplete.
2 | Regulatory Query Handling |  | 100% | [6 empty] | Not software — Regulatory query handling is a service duty, not software.
3 | Employee & Case Management |  | 100% | [6 empty] | Partial — Absence cases and ticket threads exist; no grievance/POSH case management screens.
10. Process Related to Final Settlement Processing
10.1 Process Related to Final settlement Process:
1 | Settlement Input in Excel Format as shared by Protiviti viz – Number of days payable, Salary hold release, Leave Encashment days/Notice Pay recovery, Other Payments& Deductions, Gratuity, LTA claimed in previous employment |  | 50% | 2025-08-31 | 1st FnF will be process in AUg 25 |  |  |  |  | Partial — F&F computed in HRMS (days, encashment, notice, gratuity); no Excel settlement input format.
2 | Communication Protocol: SFTP/ Protiviti’s CRM/ Rashmi Metaliks Limited Portal |  | 100% | [6 empty] | Not software — Communication protocol decision, not a software feature.
3 | Rashmi Metaliks Limited Employees to update investment proofs in ESS portal and submit any pending reimbursement claims |  | 100% | [6 empty] | Partial — Employees can upload investment proofs and claims; claims blocked without budget.
4 | Protiviti should process payroll based on clarifications received (post verification of investment proofs and reimbursement claims submitted) and share the Final Settlement workings for confirmation |  | 50% |  | 1st FnF will be process in AUg 25 |  |  |  |  | Partial — F&F workings computed for review; F&F can be paid twice (fix not on main).
5 | On receipt of confirmation, the following deliverables to be shared with the Rashmi Metaliks Limited SPOC |  | 50% | [6 empty] | Partial — Relieving letter and service certificate issued on F&F payment; duplicate-payment bug open.
10.2 Full and Final Settlement Process-General
1 | Protiviti should offers 2 Full and Final cycle. |  | 50% |  | 1st FnF will be process in AUg 25 |  |  |  |  | Missing — No F&F cycle calendar; system can't model two F&F cycles per month.
2 | The turnaround time to process Full and Final is 3 working days. |  | 50% | [6 empty] | Missing — No turnaround-time tracking for F&F processing.
3 | Protiviti would not interact with resigned employees and details would be shared only to SPOC. |  | 50% | [6 empty] | Not software — Vendor communication rule, not software.
4 | “Alumni portal” access to exit employees need to be confirmedly Rashmi Metaliks Limited for RML to download |  | 50% | [6 empty] | Partial — Alumni portal page exists; shows a hard-coded gratuity figure (fix not on main).
Total percentage completed